## Tasks
UniqueID | ID | Name | Notes | ResourceNames | Start | Finish | PercentComplete
1 | 1 | Three-story Office Building (76,000 square feet) |  | 未割り当て | 946854000000 | 988272000000 | 1.0172
2 | 2 | General Conditions |  | 未割り当て | 946854000000 | 948787200000 | 6.8182
3 | 3 | Receive notice to proceed and sign contract |  | G.C. General Management | 946854000000 | 947059200000 | 100
4 | 4 | Submit bond and insurance documents |  | G.C. Project Management,G.C. General Management | 946854000000 | 946972800000 | 0
5 | 5 | Prepare and submit project schedule |  | G.C. Project Management,G.C. Scheduler | 947026800000 | 947145600000 | 0
6 | 6 | Prepare and submit schedule of values |  | G.C. General Management,G.C. Project Management | 947199600000 | 947491200000 | 0
7 | 7 | Obtain building permits |  | G.C. Project Management,G.C. Procurement | 947113200000 | 947577600000 | 0
8 | 8 | Submit preliminary shop drawings |  | G.C. Project Management,G.C. Procurement | 947631600000 | 948787200000 | 0
9 | 9 | Submit monthly requests for payment | Monthly requests for payment can be entered as a recurring task. See the Help topic "Enter a recurring task." | 未割り当て | 947113200000 | 947145600000 | 0
10 | 10 | Long Lead Procurement |  | 未割り当て | 947199600000 | 955612800000 | 5.5556
11 | 11 | Submit shop drawings and order long lead items - steel |  | Steel Erection Contractor Management | 947199600000 | 948355200000 | 0
12 | 12 | Submit shop drawings and order long lead items - roofing |  | Roofing Contractor Management | 948841200000 | 949996800000 | 0
13 | 13 | Submit shop drawings and order long lead items - elevator |  | Elevator Contractor Management | 948841200000 | 949996800000 | 100
14 | 14 | Submit shop drawings and order long lead items - plumbing |  | Plumbing Contractor Management | 948841200000 | 949996800000 | 0
15 | 15 | Submit shop drawings and order long lead items - electric |  | Electric Contractor Management | 948841200000 | 949996800000 | 0
16 | 16 | Submit shop drawings and order long lead items - HVAC |  | HVAC Contractor Management | 948841200000 | 949996800000 | 0
17 | 17 | Detail, fabricate and deliver steel |  | Steel Erection Contractor Management,Steel Erection Contractor | 948409200000 | 955612800000 | 0
18 | 18 | Mobilize on Site |  | 未割り当て | 947113200000 | 948268800000 | 0
19 | 19 | Install temporary power |  | Electric Contractor | 947113200000 | 947232000000 | 0
20 | 20 | Install temporary water service |  | Plumbing Contractor | 947113200000 | 947232000000 | 0
21 | 21 | Set up site office |  | G.C. Superintendent,G.C. Labor Crew | 947458800000 | 947664000000 | 0
22 | 22 | Set line and grade benchmarks |  | G.C. Survey Crew | 947718000000 | 948096000000 | 0
23 | 23 | Prepare site - lay down yard and temporary fencing |  | Site Grading Contractor,G.C. Labor Crew | 948150000000 | 948268800000 | 0
24 | 24 | Site Grading and Utilities |  | 未割り当て | 948322800000 | 952502400000 | 0
25 | 25 | Clear and grub site |  | Site Grading Contractor | 948322800000 | 948700800000 | 0
26 | 26 | Stone site access and temporary parking area |  | Site Grading Contractor | 948754800000 | 948873600000 | 0
27 | 27 | Rough grade site (cut and fill) |  | Site Grading Contractor | 948927600000 | 949478400000 | 0
28 | 28 | Install storm drainage |  | Site Grading Contractor | 949532400000 | 950688000000 | 0
29 | 29 | Install exterior fire line and building fire riser |  | Plumbing Contractor | 949532400000 | 950688000000 | 0
30 | 30 | Perform final site grading |  | Site Grading Contractor | 950742000000 | 951897600000 | 0
31 | 31 | Erect building batter boards and layout building |  | G.C. Survey Crew | 951951600000 | 952502400000 | 0
32 | 32 | Foundations |  | 未割り当て | 952556400000 | 956563200000 | 0
33 | 33 | Excavate foundations |  | Site Grading Contractor | 952556400000 | 953712000000 | 0
34 | 34 | Excavate elevator pit |  | Site Grading Contractor | 952556400000 | 952675200000 | 0
35 | 35 | Form column piers and spread foundations |  | G.C. Rough Carpenter Crew | 953766000000 | 954230400000 | 0
36 | 36 | Rough-in electric and plumbing in elevator |  | Plumbing Contractor,Electric Contractor | 952902000000 | 953193600000 | 0
37 | 37 | Form elevator pit walls |  | G.C. Rough Carpenter Crew | 953247600000 | 953712000000 | 0
38 | 38 | Set reinforcing and anchor bolts |  | G.C. Rough Carpenter Crew | 954284400000 | 954748800000 | 0
39 | 39 | Pour column piers and foundations |  | G.C. Concrete Crew | 954802800000 | 955353600000 | 0
40 | 40 | Pour concrete elevator walls |  | G.C. Concrete Crew | 953766000000 | 953798400000 | 0
41 | 41 | Cure elevator wall concrete |  | G.C. Labor Crew | 953852400000 | 954748800000 | 0
42 | 42 | Cure piers and foundations |  | G.C. Labor Crew | 955407600000 | 956131200000 | 0
43 | 43 | Strip wall forms |  | G.C. Labor Crew | 954802800000 | 954835200000 | 0
44 | 44 | Strip column piers and foundation forms |  | G.C. Labor Crew | 956185200000 | 956563200000 | 0
45 | 45 | Install pneumatic tube in elevator pit |  | Elevator Contractor | 954889200000 | 955094400000 | 0
46 | 46 | Prepare and pour concrete floor in elevator pit |  | G.C. Concrete Crew | 955321200000 | 955353600000 | 0
47 | 47 | Steel Erection |  | 未割り当て | 956617200000 | 962006400000 | 0
48 | 48 | Erect steel columns, beams and joist - 1st and 2nd floors |  | Steel Erection Contractor | 956617200000 | 957772800000 | 0
49 | 49 | Erect steel columns, beams and joist - 3rd floor and roof |  | Steel Erection Contractor | 957826800000 | 958982400000 | 0
50 | 50 | Install miscellaneous iron and bracing - 1st and 2nd floors |  | Steel Erection Contractor | 957826800000 | 958982400000 | 0
51 | 51 | Install miscellaneous iron and bracing - 3rd floor and roof |  | Steel Erection Contractor | 959036400000 | 960192000000 | 0
52 | 52 | Install stairs and miscellaneous iron railing |  | Steel Erection Contractor | 960246000000 | 961401600000 | 0
53 | 53 | Touch-up paint on steel |  | Steel Erection Contractor | 961455600000 | 962006400000 | 0
54 | 54 | Form and Pour Concrete - Floors and Roof |  | 未割り当て | 957826800000 | 968054400000 | 0
55 | 55 | Form 2nd floor including all floor openings |  | G.C. Rough Carpenter Crew,G.C. Labor Crew | 962060400000 | 962611200000 | 0
56 | 56 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) |  | G.C. Labor Crew,Plumbing Contractor,Electric Contractor | 957826800000 | 958377600000 | 0
57 | 57 | Pour 2nd floor slab |  | G.C. Concrete Crew | 962665200000 | 962956800000 | 0
58 | 58 | Cure 2nd floor slab |  | G.C. Labor Crew | 963183600000 | 963907200000 | 0
59 | 59 | Strip forms from 2nd floor slab |  | G.C. Labor Crew | 963961200000 | 964080000000 | 0
60 | 60 | Form 3rd floor including all floor openings |  | G.C. Rough Carpenter Crew,G.C. Labor Crew | 963961200000 | 964512000000 | 0
61 | 61 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) |  | G.C. Labor Crew,Plumbing Contractor,Electric Contractor | 963961200000 | 964512000000 | 0
62 | 62 | Pour 3rd floor slab |  | G.C. Concrete Crew | 964566000000 | 965030400000 | 0
63 | 63 | Cure 3rd floor slab |  | G.C. Labor Crew | 965084400000 | 965808000000 | 0
64 | 64 | Strip forms from 3rd floor slab |  | G.C. Labor Crew | 965862000000 | 965980800000 | 0
65 | 65 | Form roof slab including all floor openings |  | G.C. Rough Carpenter Crew,G.C. Labor Crew | 965862000000 | 966412800000 | 0
66 | 66 | Install rebar and in-floor utilities (including mechanical, electrical, plumbing) |  | G.C. Labor Crew,Plumbing Contractor,Electric Contractor | 965862000000 | 966412800000 | 0
67 | 67 | Pour roof slab |  | G.C. Concrete Crew | 966466800000 | 966931200000 | 0
68 | 68 | Cure roof slab |  | G.C. Labor Crew | 966985200000 | 967708800000 | 0
69 | 69 | Strip forms from roof slab |  | G.C. Labor Crew | 967762800000 | 968054400000 | 0
70 | 70 | Form 1st floor |  | G.C. Rough Carpenter Crew | 964134000000 | 964598400000 | 0
71 | 71 | Install electrical underground |  | Electric Contractor | 964134000000 | 964684800000 | 0
72 | 72 | Install plumbing underground |  | Plumbing Contractor | 964134000000 | 964684800000 | 0
73 | 73 | Install rebar and in-floor utilities |  | G.C. Labor Crew,Plumbing Contractor,Electric Contractor | 964134000000 | 964598400000 | 0
74 | 74 | Pour 1st floor slab |  | G.C. Concrete Crew | 964738800000 | 965203200000 | 0
75 | 75 | Cure 1st floor slab |  | G.C. Labor Crew | 965257200000 | 965980800000 | 0
76 | 76 | Strip forms from 1st floor slab |  | G.C. Labor Crew | 966207600000 | 966326400000 | 0
77 | 77 | Carpentry Work |  | 未割り当て | 968108400000 | 969868800000 | 0
78 | 78 | Install exterior sheathing and metal studs |  | Drywall Contractor | 968108400000 | 969868800000 | 0
79 | 79 | Masonry Work |  | 未割り当て | 960246000000 | 973497600000 | 0
80 | 80 | Rough-in plumbing at toilets and masonry walls |  | Plumbing Contractor | 966380400000 | 968745600000 | 0
81 | 81 | Lay masonry at core, mechanical, and toilets |  | Masonry Contractor | 960246000000 | 962611200000 | 0
82 | 82 | Install exterior masonry work |  | Masonry Contractor | 969922800000 | 972892800000 | 0
83 | 83 | Install roof drains |  | Roofing Contractor | 972946800000 | 973065600000 | 0
84 | 84 | Install tile in toilet rooms |  | Tile Contractor | 968799600000 | 969955200000 | 0
85 | 85 | Clean masonry |  | Masonry Contractor | 972946800000 | 973497600000 | 0
86 | 86 | Clean toilet room tile |  | Tile Contractor | 970009200000 | 970560000000 | 0
87 | 87 | Roofing |  | 未割り当て | 972946800000 | 976608000000 | 0
88 | 88 | Install flashing at parapet walls |  | Roofing Contractor | 972946800000 | 973238400000 | 0
89 | 89 | Pour lightweight concrete roof fill |  | Roofing Contractor | 973465200000 | 973584000000 | 0
90 | 90 | Install seamless roofing material |  | Roofing Contractor | 974242800000 | 974793600000 | 0
91 | 91 | Spread stone ballast on seamless roof |  | Roofing Contractor | 974847600000 | 975398400000 | 0
92 | 92 | Set rooftop equipment |  | HVAC Contractor | 975452400000 | 976608000000 | 0
93 | 93 | Window wall and store front closures |  | 未割り当て | 972946800000 | 980150400000 | 0
94 | 94 | Install window wall aluminum and glass |  | Window Contractor | 972946800000 | 975916800000 | 0
95 | 95 | Install interior stud walls and drywall |  | Drywall Contractor | 975970800000 | 978940800000 | 0
96 | 96 | Install interior doors and hardware |  | G.C. Finish Carpenter Crew | 978994800000 | 980150400000 | 0
97 | 97 | Install store front doors and hardware |  | Window Contractor | 972946800000 | 974707200000 | 0
98 | 98 | Building Finishes |  | 未割り当て | 975970800000 | 985593600000 | 0
99 | 99 | Install millwork and wood trim |  | G.C. Finish Carpenter Crew | 978994800000 | 980755200000 | 0
100 | 100 | Paint walls and woodwork |  | Painting Contractor | 980809200000 | 983174400000 | 0
101 | 101 | Install conduit at ceiling plenum space |  | Electric Contractor | 975970800000 | 977731200000 | 0
102 | 102 | Install duct in ceiling plenum space |  | HVAC Contractor | 978994800000 | 980755200000 | 0
103 | 103 | Install ceiling grid |  | Drywall Contractor | 980809200000 | 981964800000 | 0
104 | 104 | Install ceiling tile |  | Drywall Contractor | 982018800000 | 983174400000 | 0
105 | 105 | Hang wallpaper |  | Painting Contractor | 982018800000 | 983174400000 | 0
106 | 106 | Install building carpet |  | Carpet Contractor | 983228400000 | 985593600000 | 0
107 | 107 | Install hardware and accessories |  | G.C. Finish Carpenter Crew | 983228400000 | 984988800000 | 0
108 | 108 | Complete interior and exterior sod and plantings |  | Landscape Contractor | 983228400000 | 984384000000 | 0
109 | 109 | Pave, curb, and stripe parking lot |  | Paving Contractor | 984438000000 | 985593600000 | 0
110 | 110 | Elevators |  | 未割り当て | 962665200000 | 967449600000 | 0
111 | 111 | Set elevator equipment in shafts |  | Elevator Contractor | 962665200000 | 965030400000 | 0
112 | 112 | Set equipment in mechanical room |  | Elevator Contractor | 965084400000 | 966240000000 | 0
113 | 113 | Test and align doors and equipment |  | Elevator Contractor | 966294000000 | 967449600000 | 0
114 | 114 | Plumbing |  | 未割り当て | 973551600000 | 984384000000 | 0
115 | 115 | Rough-in plumbing in drywall walls |  | Plumbing Contractor | 975970800000 | 978336000000 | 0
116 | 116 | Tie-in fire line riser and set valves |  | Plumbing Contractor | 973551600000 | 974707200000 | 0
117 | 117 | Set plumbing fixtures and trim |  | Plumbing Contractor | 978390000000 | 980150400000 | 0
118 | 118 | Flush, test, and clean piping and fixtures |  | Plumbing Contractor | 983228400000 | 984384000000 | 0
119 | 119 | Electrical |  | 未割り当て | 966380400000 | 983174400000 | 0
120 | 120 | Rough-in electrical in masonry walls |  | Electric Contractor | 966380400000 | 968745600000 | 0
121 | 121 | Rough-in electrical in drywall walls |  | Electric Contractor | 975970800000 | 978336000000 | 0
122 | 122 | Pull wire in conduit and set area transformers |  | Electric Contractor | 977785200000 | 979545600000 | 0
123 | 123 | Install and terminate electrical devices |  | Electric Contractor | 979599600000 | 981360000000 | 0
124 | 124 | Make electrical terminations for HVAC equipment |  | Electric Contractor | 979599600000 | 979718400000 | 0
125 | 125 | Install light fixtures - test and clean |  | Electric Contractor | 982018800000 | 983174400000 | 0
126 | 126 | Heating and Ventilating - AC |  | 未割り当て | 962665200000 | 984384000000 | 0
127 | 127 | Set equipment in mechanical room |  | HVAC Contractor | 962665200000 | 963820800000 | 0
128 | 128 | Rough-in mechanical in masonry walls |  | HVAC Contractor | 966380400000 | 968745600000 | 0
129 | 129 | Rough-in mechanical in drywall walls |  | HVAC Contractor | 975970800000 | 977126400000 | 0
130 | 130 | Install duct in building chase |  | HVAC Contractor | 975970800000 | 977731200000 | 0
131 | 131 | Set HVAC trim and test and balance system |  | HVAC Contractor | 982018800000 | 984384000000 | 0
132 | 132 | Final Clean-up and Occupancy |  | 未割り当て | 978994800000 | 986198400000 | 0
133 | 133 | Install hard tile flooring in common areas |  | Tile Contractor | 978994800000 | 979545600000 | 0
134 | 134 | Clean hard tile floors |  | Tile Contractor | 979599600000 | 979891200000 | 0
135 | 135 | Remove debris from building and do final clean-up |  | G.C. Labor Crew | 985647600000 | 985939200000 | 0
136 | 136 | Substantial completion date |  | G.C. Superintendent | 986166000000 | 986198400000 | 0
137 | 137 | Complete Final Inspections |  | 未割り当て | 986166000000 | 986803200000 | 0
138 | 138 | Complete elevator inspection and certification |  | Elevator Contractor | 986166000000 | 986371200000 | 0
139 | 139 | Perform architect's inspection |  | G.C. Superintendent,G.C. Project Management | 986425200000 | 986457600000 | 0
140 | 140 | Perform local building agency inspection |  | G.C. Project Management,G.C. Superintendent | 986511600000 | 986544000000 | 0
141 | 141 | Perform Fire Marshal's inspection |  | G.C. Superintendent,G.C. Project Management | 986770800000 | 986803200000 | 0
142 | 142 | Complete punch list items from all inspections |  | G.C. Superintendent,G.C. Labor Crew,Plumbing Contractor,Electric Contractor,HVAC Contractor,Drywall Contractor,Carpet Contractor,Paving Contractor,Painting Contractor | 986857200000 | 988012800000 | 0
143 | 143 | Obtain certificate of occupancy |  | G.C. Project Management | 988066800000 | 988185600000 | 0
144 | 144 | Issue final completion documents including warranties |  | G.C. Project Management | 988066800000 | 988099200000 | 0
145 | 145 | Issue final request for payment |  | G.C. Project Management,G.C. Accounting,G.C. General Management | 988239600000 | 988272000000 | 0

## _ProjectLibre_MSPDI (hidden)
MSPDI XML
<?xml version="1.0" encoding="UTF-8" standalone="yes"?> <Project xmlns="http://schemas.microsoft.com/project"> <SaveVersion>14</SaveVersion> <Name></Name> <Title></Title> <Manager></Manager> <ScheduleFromStart>1</ScheduleFromStart> <StartDate>2000-01-03T08:00:00</StartDate> <FinishDate>2001-04-26T17:00:00</FinishDate> <FYStartDate>1</FYStartDate> <CriticalSlackLimit>0</CriticalSlackLimit> <CurrencyDigits>2</CurrencyDigits> <CurrencySymbol>$</CurrencySymbol> <CurrencySymbolPosition>0</CurrencySymbolPosition> <CalendarUID>1</CalendarUID> <DefaultStartTime>17:00:00</DefaultStartTime> <DefaultFinishTime>02:00:00</DefaultFinishTime> <MinutesPerDay>480</MinutesPerDay> <MinutesPerWeek>2400</MinutesPerWeek> <DaysPerMonth>20</DaysPerMonth> <DefaultTaskType>0</DefaultTaskType> <DefaultFixedCostAccrual>2</DefaultFixedCostAccrual> <DefaultStandardRate>10</DefaultStandardRate> <DefaultOvertimeRate>15</DefaultOvertimeRate> <DurationFormat>7</DurationFormat> <WorkFormat>2</WorkFormat> <EditableActualCosts>0</EditableActualCosts> <HonorConstraints>0</HonorConstraints> <EarnedValueMethod>0</EarnedValueMethod> <InsertedProjectsLikeSummary>0</InsertedProjectsLikeSummary> <MultipleCriticalPaths>0</MultipleCriticalPaths> <NewTasksEffortDriven>0</NewTasksEffortDriven> <NewTasksEstimated>1</NewTasksEstimated> <SplitsInProgressTasks>0</SplitsInProgressTasks> <SpreadActualCost>0</SpreadActualCost> <SpreadPercentComplete>0</SpreadPercentComplete> <TaskUpdatesResource>1</TaskUpdatesResource> <FiscalYearStart>0</FiscalYearStart> <WeekStartDay>1</WeekStartDay> <MoveCompletedEndsBack>0</MoveCompletedEndsBack> <MoveRemainingStartsBack>0</MoveRemainingStartsBack> <MoveRemainingStartsForward>0</MoveRemainingStartsForward> <MoveCompletedEndsForward>0</MoveCompletedEndsForward> <BaselineForEarnedValue>0</BaselineForEarnedValue> <AutoAddNewResourcesAndTasks>1</AutoAddNewResourcesAndTasks> <CurrentDate>2026-06-04T07:06:40</CurrentDate> <MicrosoftProjectServerURL>1</MicrosoftProjectServerURL> <Autolink>1</Autolink> <NewTaskStartDate>0</NewTaskStartDate> <DefaultTaskEVMethod>0</DefaultTaskEVMethod> <ProjectExternallyEdited>0</ProjectExternallyEdited> <ActualsInSync>0</ActualsInSync> <RemoveFileProperties>0</RemoveFileProperties> <AdminProject>0</AdminProject> <NewTasksAreManual>1</NewTasksAreManual> <ExtendedAttributes/> <Calendars> <Calendar> <UID>1</UID> <Name>Standard[Imported]</Name> <IsBaseCalendar>1</IsBaseCalendar> <BaseCalendarUID>-1</BaseCalendarUID> <WeekDays> <WeekDay> <DayType>1</DayType> <DayWorking>0</DayWorking> </WeekDay> <WeekDay> <DayType>2</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>08:00:00</FromTime> <ToTime>12:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>13:00:00</FromTime> <ToTime>17:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>3</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>08:00:00</FromTime> <ToTime>12:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>13:00:00</FromTime> <ToTime>17:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>4</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>08:00:00</FromTime> <ToTime>12:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>13:00:00</FromTime> <ToTime>17:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>5</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>08:00:00</FromTime> <ToTime>12:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>13:00:00</FromTime> <ToTime>17:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>6</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>08:00:00</FromTime> <ToTime>12:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>13:00:00</FromTime> <ToTime>17:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>7</DayType> <DayWorking>0</DayWorking> </WeekDay> </WeekDays> </Calendar> <Calendar> <UID>2</UID> <Name>標準</Name> <IsBaseCalendar>1</IsBaseCalendar> <BaseCalendarUID>-1</BaseCalendarUID> <WeekDays> <WeekDay> <DayType>1</DayType> <DayWorking>0</DayWorking> </WeekDay> <WeekDay> <DayType>2</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>08:00:00</FromTime> <ToTime>12:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>13:00:00</FromTime> <ToTime>17:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>3</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>08:00:00</FromTime> <ToTime>12:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>13:00:00</FromTime> <ToTime>17:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>4</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>08:00:00</FromTime> <ToTime>12:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>13:00:00</FromTime> <ToTime>17:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>5</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>08:00:00</FromTime> <ToTime>12:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>13:00:00</FromTime> <ToTime>17:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>6</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>08:00:00</FromTime> <ToTime>12:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>13:00:00</FromTime> <ToTime>17:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>7</DayType> <DayWorking>0</DayWorking> </WeekDay> </WeekDays> </Calendar> <Calendar> <UID>3</UID> <Name>24 時間</Name> <IsBaseCalendar>1</IsBaseCalendar> <BaseCalendarUID>-1</BaseCalendarUID> <WeekDays> <WeekDay> <DayType>1</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>2</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>3</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>4</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>5</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>6</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>7</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> </WeekDays> </Calendar> <Calendar> <UID>4</UID> <Name>夜間作業</Name> <IsBaseCalendar>1</IsBaseCalendar> <BaseCalendarUID>-1</BaseCalendarUID> <WeekDays> <WeekDay> <DayType>1</DayType> <DayWorking>0</DayWorking> </WeekDay> <WeekDay> <DayType>2</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>23:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>3</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>03:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>04:00:00</FromTime> <ToTime>08:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>23:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>4</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>03:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>04:00:00</FromTime> <ToTime>08:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>23:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>5</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>03:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>04:00:00</FromTime> <ToTime>08:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>23:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>6</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>03:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>04:00:00</FromTime> <ToTime>08:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>23:00:00</FromTime> <ToTime>00:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> <WeekDay> <DayType>7</DayType> <DayWorking>1</DayWorking> <WorkingTimes> <WorkingTime> <FromTime>00:00:00</FromTime> <ToTime>03:00:00</ToTime> </WorkingTime> <WorkingTime> <FromTime>04:00:00</FromTime> <ToTime>08:00:00</ToTime> </WorkingTime> </WorkingTimes> </WeekDay> </WeekDays> </Calendar> <Calendar> <UID>5</UID> <Name>G.C. General Management</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>6</UID> <Name>G.C. Project Management</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>7</UID> <Name>G.C. Procurement</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>8</UID> <Name>G.C. Scheduler</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>9</UID> <Name>G.C. Accounting</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>10</UID> <Name>G.C. Superintendent</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>11</UID> <Name>G.C. Survey Crew</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>12</UID> <Name>G.C. Rough Carpenter Crew</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>13</UID> <Name>G.C. Labor Crew</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>14</UID> <Name>G.C. Concrete Crew</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>15</UID> <Name>G.C. Finish Carpenter Crew</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>16</UID> <Name>Site Grading Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>17</UID> <Name>Plumbing Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>18</UID> <Name>Plumbing Contractor Management</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>19</UID> <Name>Electric Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>20</UID> <Name>Electric Contractor Management</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>21</UID> <Name>HVAC Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>22</UID> <Name>HVAC Contractor Management</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>23</UID> <Name>Elevator Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>24</UID> <Name>Elevator Contractor Management</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>25</UID> <Name>Steel Erection Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>26</UID> <Name>Steel Erection Contractor Management</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>27</UID> <Name>Drywall Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>28</UID> <Name>Masonry Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>29</UID> <Name>Tile Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>30</UID> <Name>Roofing Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>31</UID> <Name>Roofing Contractor Management</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>32</UID> <Name>Window Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>33</UID> <Name>Carpet Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>34</UID> <Name>Landscape Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>35</UID> <Name>Paving Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> <Calendar> <UID>36</UID> <Name>Painting Contractor</Name> <IsBaseCalendar>0</IsBaseCalendar> <BaseCalendarUID>2</BaseCalendarUID> </Calendar> </Calendars> <Tasks> <Task> <UID>1</UID> <ID>1</ID> <Name>Three-story Office Building (76,000 square feet)</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1</WBS> <OutlineNumber>1</OutlineNumber> <OutlineLevel>1</OutlineLevel> <Priority>500</Priority> <Start>2000-01-03T08:00:00</Start> <Finish>2001-04-26T17:00:00</Finish> <Duration>PT2752H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>1</PercentComplete> <PercentWorkComplete>1</PercentWorkComplete> <RemainingDuration>PT2724H0M23S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>2</UID> <ID>2</ID> <Name>General Conditions</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.1</WBS> <OutlineNumber>1.1</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-01-03T08:00:00</Start> <Finish>2000-01-25T17:00:00</Finish> <Duration>PT136H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1569600</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>7</PercentComplete> <PercentWorkComplete>12</PercentWorkComplete> <RemainingDuration>PT126H43M38S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>3</UID> <ID>3</ID> <Name>Receive notice to proceed and sign contract</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.1.1</WBS> <OutlineNumber>1.1.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-03T08:00:00</Start> <Finish>2000-01-05T17:00:00</Finish> <Duration>PT24H0M0S</Duration> <DurationFormat>7</DurationFormat> <Stop>2000-01-05T17:00:00</Stop> <Resume>2000-01-06T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>100</PercentComplete> <PercentWorkComplete>100</PercentWorkComplete> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>4</UID> <ID>4</ID> <Name>Submit bond and insurance documents</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.1.2</WBS> <OutlineNumber>1.1.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-03T08:00:00</Start> <Finish>2000-01-04T17:00:00</Finis
h> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1622400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>5</UID> <ID>5</ID> <Name>Prepare and submit project schedule</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.1.3</WBS> <OutlineNumber>1.1.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-05T08:00:00</Start> <Finish>2000-01-06T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-05T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1622400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>4</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>6</UID> <ID>6</ID> <Name>Prepare and submit schedule of values</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.1.4</WBS> <OutlineNumber>1.1.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-07T08:00:00</Start> <Finish>2000-01-10T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-07T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1622400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>5</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>7</UID> <ID>7</ID> <Name>Obtain building permits</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.1.5</WBS> <OutlineNumber>1.1.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-06T08:00:00</Start> <Finish>2000-01-11T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-06T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>3</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>8</UID> <ID>8</ID> <Name>Submit preliminary shop drawings</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.1.6</WBS> <OutlineNumber>1.1.6</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-12T08:00:00</Start> <Finish>2000-01-25T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-12T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>7</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>9</UID> <ID>9</ID> <Name>Submit monthly requests for payment</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.1.7</WBS> <OutlineNumber>1.1.7</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-06T08:00:00</Start> <Finish>2000-01-06T17:00:00</Finish> <Duration>PT8H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-06T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>33600</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT8H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <Notes>Monthly requests for payment can be entered as a recurring task. See the Help topic "Enter a recurring task." </Notes> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>3</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>10</UID> <ID>10</ID> <Name>Long Lead Procurement</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.2</WBS> <OutlineNumber>1.2</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-01-07T08:00:00</Start> <Finish>2000-04-13T17:00:00</Finish> <Duration>PT560H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1060800</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>6</PercentComplete> <PercentWorkComplete>8</PercentWorkComplete> <RemainingDuration>PT528H53M20S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>11</UID> <ID>11</ID> <Name>Submit shop drawings and order long lead items - steel</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.2.1</WBS> <OutlineNumber>1.2.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-07T08:00:00</Start> <Finish>2000-01-20T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-07T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>33600</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>9</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>12</UID> <ID>12</ID> <Name>Submit shop drawings and order long lead items - roofing</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.2.2</WBS> <OutlineNumber>1.2.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-26T08:00:00</Start> <Finish>2000-02-08T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-26T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1286400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>8</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>13</UID> <ID>13</ID> <Name>Submit shop drawings and order long lead items - elevator</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.2.3</WBS> <OutlineNumber>1.2.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-26T08:00:00</Start> <Finish>2000-02-08T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Stop>2000-02-08T17:00:00</Stop> <Resume>2000-02-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1238400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>100</PercentComplete> <PercentWorkComplete>100</PercentWorkComplete> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>8</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>14</UID> <ID>14</ID> <Name>Submit shop drawings and order long lead items - plumbing</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.2.4</WBS> <OutlineNumber>1.2.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-26T08:00:00</Start> <Finish>2000-02-08T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-26T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>8</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>15</UID> <ID>15</ID> <Name>Submit shop drawings and order long lead items - electric</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.2.5</WBS> <OutlineNumber>1.2.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-26T08:00:00</Start> <Finish>2000-02-08T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-26T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>8</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>16</UID> <ID>16</ID> <Name>Submit shop drawings and order long lead items - HVAC</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.2.6</WBS> <OutlineNumber>1.2.6</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-26T08:00:00</Start> <Finish>2000-02-08T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-26T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>8</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>17</UID> <ID>17</ID> <Name>Detail, fabricate and deliver steel</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.2.7</WBS> <OutlineNumber>1.2.7</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-21T08:00:00</Start> <Finish>2000-04-13T17:00:00</Finish> <Duration>PT480H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-21T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>33600</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT480H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <
HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>11</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>18</UID> <ID>18</ID> <Name>Mobilize on Site</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.3</WBS> <OutlineNumber>1.3</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-01-06T08:00:00</Start> <Finish>2000-01-19T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>19</UID> <ID>19</ID> <Name>Install temporary power</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.3.1</WBS> <OutlineNumber>1.3.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-06T08:00:00</Start> <Finish>2000-01-07T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-06T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>3</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>20</UID> <ID>20</ID> <Name>Install temporary water service</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.3.2</WBS> <OutlineNumber>1.3.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-06T08:00:00</Start> <Finish>2000-01-07T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-06T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>3</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>21</UID> <ID>21</ID> <Name>Set up site office</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.3.3</WBS> <OutlineNumber>1.3.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-10T08:00:00</Start> <Finish>2000-01-12T17:00:00</Finish> <Duration>PT24H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-10T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT24H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>19</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>20</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>22</UID> <ID>22</ID> <Name>Set line and grade benchmarks</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.3.4</WBS> <OutlineNumber>1.3.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-13T08:00:00</Start> <Finish>2000-01-17T17:00:00</Finish> <Duration>PT24H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-13T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT24H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>21</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>23</UID> <ID>23</ID> <Name>Prepare site - lay down yard and temporary fencing</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.3.5</WBS> <OutlineNumber>1.3.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-18T08:00:00</Start> <Finish>2000-01-19T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-18T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>22</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>24</UID> <ID>24</ID> <Name>Site Grading and Utilities</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.4</WBS> <OutlineNumber>1.4</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-01-20T08:00:00</Start> <Finish>2000-03-08T17:00:00</Finish> <Duration>PT280H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT280H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>25</UID> <ID>25</ID> <Name>Clear and grub site</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.4.1</WBS> <OutlineNumber>1.4.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-20T08:00:00</Start> <Finish>2000-01-24T17:00:00</Finish> <Duration>PT24H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-20T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT24H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>21</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>23</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>26</UID> <ID>26</ID> <Name>Stone site access and temporary parking area</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.4.2</WBS> <OutlineNumber>1.4.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-25T08:00:00</Start> <Finish>2000-01-26T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-25T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>25</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>23</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>27</UID> <ID>27</ID> <Name>Rough grade site (cut and fill)</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.4.3</WBS> <OutlineNumber>1.4.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-01-27T08:00:00</Start> <Finish>2000-02-02T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-27T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>26</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>28</UID> <ID>28</ID> <Name>Install storm drainage</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.4.4</WBS> <OutlineNumber>1.4.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-02-03T08:00:00</Start> <Finish>2000-02-16T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-02-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>43200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>27</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>29</UID> <ID>29</ID> <Name>Install exterior fire line and building fire riser</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.4.5</WBS> <OutlineNumber>1.4.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-02-03T08:00:00</Start> <Finish>2000-02-16T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-02-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>27</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>30</UID> <ID>30</ID> <Name>Perform final site grading</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.4.6</WBS> <OutlineNumber>1.4.6</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-02-17T08:00:00</Start> <Finish>2000-03-01T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-02-17T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>28</PredecessorUID> <Type>0</Type> <CrossProject>0</CrossProject> <LinkLag>4800</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>29</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>31</UID> <ID>31</ID> <Name>Erect building batter boards and layout building</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.4.7</WBS> <OutlineNumber>1.4.7</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-03-02T08:00:00</Start> <Finish>2000-03-08T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationF
ormat>7</DurationFormat> <Resume>2000-03-02T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>30</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>32</UID> <ID>32</ID> <Name>Foundations</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5</WBS> <OutlineNumber>1.5</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-03-09T08:00:00</Start> <Finish>2000-04-24T17:00:00</Finish> <Duration>PT264H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>979200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT264H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>33</UID> <ID>33</ID> <Name>Excavate foundations</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.1</WBS> <OutlineNumber>1.5.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-03-09T08:00:00</Start> <Finish>2000-03-22T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-03-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>31</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>34</UID> <ID>34</ID> <Name>Excavate elevator pit</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.2</WBS> <OutlineNumber>1.5.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-03-09T08:00:00</Start> <Finish>2000-03-10T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-03-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1027200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>31</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>35</UID> <ID>35</ID> <Name>Form column piers and spread foundations</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.3</WBS> <OutlineNumber>1.5.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-03-23T08:00:00</Start> <Finish>2000-03-28T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-03-23T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>33</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>36</UID> <ID>36</ID> <Name>Rough-in electric and plumbing in elevator</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.4</WBS> <OutlineNumber>1.5.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-03-13T08:00:00</Start> <Finish>2000-03-16T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-03-13T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1027200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>34</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>37</UID> <ID>37</ID> <Name>Form elevator pit walls</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.5</WBS> <OutlineNumber>1.5.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-03-17T08:00:00</Start> <Finish>2000-03-22T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-03-17T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1027200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>36</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>38</UID> <ID>38</ID> <Name>Set reinforcing and anchor bolts</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.6</WBS> <OutlineNumber>1.5.6</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-03-29T08:00:00</Start> <Finish>2000-04-03T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-03-29T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>35</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>39</UID> <ID>39</ID> <Name>Pour column piers and foundations</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.7</WBS> <OutlineNumber>1.5.7</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-04-04T08:00:00</Start> <Finish>2000-04-10T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-04-04T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>38</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>40</UID> <ID>40</ID> <Name>Pour concrete elevator walls</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.8</WBS> <OutlineNumber>1.5.8</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-03-23T08:00:00</Start> <Finish>2000-03-23T17:00:00</Finish> <Duration>PT8H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-03-23T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1027200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT8H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>37</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>41</UID> <ID>41</ID> <Name>Cure elevator wall concrete</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.9</WBS> <OutlineNumber>1.5.9</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-03-24T08:00:00</Start> <Finish>2000-04-03T17:00:00</Finish> <Duration>PT56H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-03-24T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1027200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT56H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>40</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>42</UID> <ID>42</ID> <Name>Cure piers and foundations</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.10</WBS> <OutlineNumber>1.5.10</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-04-11T08:00:00</Start> <Finish>2000-04-19T17:00:00</Finish> <Duration>PT56H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-04-11T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT56H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>39</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>43</UID> <ID>43</ID> <Name>Strip wall forms</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.11</WBS> <OutlineNumber>1.5.11</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-04-04T08:00:00</Start> <Finish>2000-04-04T17:00:00</Finish> <Duration>PT8H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-04-04T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1027200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT8H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>41</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>44</UID> <ID>44</ID> <Name>Strip column piers and foundation forms</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.12</WBS> <OutlineNumber>1.5.12</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-04-20T08:00:00</Start> <Finish>2000-04-24T17:00:00</Finish> <Duration>PT24H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-04-20T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT24H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>42</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active>
<Manual>0</Manual> </Task> <Task> <UID>45</UID> <ID>45</ID> <Name>Install pneumatic tube in elevator pit</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.13</WBS> <OutlineNumber>1.5.13</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-04-05T08:00:00</Start> <Finish>2000-04-07T17:00:00</Finish> <Duration>PT24H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-04-05T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1027200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT24H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>43</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>46</UID> <ID>46</ID> <Name>Prepare and pour concrete floor in elevator pit</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.5.14</WBS> <OutlineNumber>1.5.14</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-04-10T08:00:00</Start> <Finish>2000-04-10T17:00:00</Finish> <Duration>PT8H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-04-10T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>1027200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT8H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>45</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>47</UID> <ID>47</ID> <Name>Steel Erection</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.6</WBS> <OutlineNumber>1.6</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-04-25T08:00:00</Start> <Finish>2000-06-26T17:00:00</Finish> <Duration>PT360H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>667200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT360H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>48</UID> <ID>48</ID> <Name>Erect steel columns, beams and joist - 1st and 2nd floors</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.6.1</WBS> <OutlineNumber>1.6.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-04-25T08:00:00</Start> <Finish>2000-05-08T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-04-25T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>44</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>17</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>49</UID> <ID>49</ID> <Name>Erect steel columns, beams and joist - 3rd floor and roof</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.6.2</WBS> <OutlineNumber>1.6.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-05-09T08:00:00</Start> <Finish>2000-05-22T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-05-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>48</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>50</UID> <ID>50</ID> <Name>Install miscellaneous iron and bracing - 1st and 2nd floors</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.6.3</WBS> <OutlineNumber>1.6.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-05-09T08:00:00</Start> <Finish>2000-05-22T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-05-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>787200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>48</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>51</UID> <ID>51</ID> <Name>Install miscellaneous iron and bracing - 3rd floor and roof</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.6.4</WBS> <OutlineNumber>1.6.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-05-23T08:00:00</Start> <Finish>2000-06-05T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-05-23T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>49</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>52</UID> <ID>52</ID> <Name>Install stairs and miscellaneous iron railing</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.6.5</WBS> <OutlineNumber>1.6.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-06-06T08:00:00</Start> <Finish>2000-06-19T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-06-06T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>51</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>53</UID> <ID>53</ID> <Name>Touch-up paint on steel</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.6.6</WBS> <OutlineNumber>1.6.6</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-06-20T08:00:00</Start> <Finish>2000-06-26T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-06-20T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>52</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>54</UID> <ID>54</ID> <Name>Form and Pour Concrete - Floors and Roof</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7</WBS> <OutlineNumber>1.7</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-05-09T08:00:00</Start> <Finish>2000-09-04T17:00:00</Finish> <Duration>PT680H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>408000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT680H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>55</UID> <ID>55</ID> <Name>Form 2nd floor including all floor openings</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.1</WBS> <OutlineNumber>1.7.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-06-27T08:00:00</Start> <Finish>2000-07-03T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-06-27T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>53</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>14</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>15</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>16</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>48</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>56</UID> <ID>56</ID> <Name>Install rebar and in-floor utilities (including mechanical, electrical, plumbing)</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.2</WBS> <OutlineNumber>1.7.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-05-09T08:00:00</Start> <Finish>2000-05-15T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-05-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>168000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>48</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>57</UID> <ID>57</ID> <Name>Pour 2nd floor slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.3</WBS> <OutlineNumber>1.7.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-04T08:00:00</Start> <Finish>2000-07-07T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-04T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>56</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>55</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task>
<UID>58</UID> <ID>58</ID> <Name>Cure 2nd floor slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.4</WBS> <OutlineNumber>1.7.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-10T08:00:00</Start> <Finish>2000-07-18T17:00:00</Finish> <Duration>PT56H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-10T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT56H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>57</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>59</UID> <ID>59</ID> <Name>Strip forms from 2nd floor slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.5</WBS> <OutlineNumber>1.7.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-19T08:00:00</Start> <Finish>2000-07-20T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-19T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>58</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>60</UID> <ID>60</ID> <Name>Form 3rd floor including all floor openings</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.6</WBS> <OutlineNumber>1.7.6</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-19T08:00:00</Start> <Finish>2000-07-25T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-19T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>58</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>61</UID> <ID>61</ID> <Name>Install rebar and in-floor utilities (including mechanical, electrical, plumbing)</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.7</WBS> <OutlineNumber>1.7.7</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-19T08:00:00</Start> <Finish>2000-07-25T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-19T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>58</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>62</UID> <ID>62</ID> <Name>Pour 3rd floor slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.8</WBS> <OutlineNumber>1.7.8</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-26T08:00:00</Start> <Finish>2000-07-31T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-26T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>61</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>60</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>63</UID> <ID>63</ID> <Name>Cure 3rd floor slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.9</WBS> <OutlineNumber>1.7.9</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-01T08:00:00</Start> <Finish>2000-08-09T17:00:00</Finish> <Duration>PT56H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-01T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT56H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>62</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>64</UID> <ID>64</ID> <Name>Strip forms from 3rd floor slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.10</WBS> <OutlineNumber>1.7.10</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-10T08:00:00</Start> <Finish>2000-08-11T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-10T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>76800</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>63</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>65</UID> <ID>65</ID> <Name>Form roof slab including all floor openings</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.11</WBS> <OutlineNumber>1.7.11</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-10T08:00:00</Start> <Finish>2000-08-16T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-10T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>63</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>66</UID> <ID>66</ID> <Name>Install rebar and in-floor utilities (including mechanical, electrical, plumbing)</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.12</WBS> <OutlineNumber>1.7.12</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-10T08:00:00</Start> <Finish>2000-08-16T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-10T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>63</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>67</UID> <ID>67</ID> <Name>Pour roof slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.13</WBS> <OutlineNumber>1.7.13</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-17T08:00:00</Start> <Finish>2000-08-22T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-17T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>66</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>65</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>68</UID> <ID>68</ID> <Name>Cure roof slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.14</WBS> <OutlineNumber>1.7.14</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-23T08:00:00</Start> <Finish>2000-08-31T17:00:00</Finish> <Duration>PT56H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-23T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT56H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>67</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>69</UID> <ID>69</ID> <Name>Strip forms from roof slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.15</WBS> <OutlineNumber>1.7.15</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-09-01T08:00:00</Start> <Finish>2000-09-04T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-09-01T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>68</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>70</UID> <ID>70</ID> <Name>Form 1st floor</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.16</WBS> <OutlineNumber>1.7.16</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-21T08:00:00</Start> <Finish>2000-07-26T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-21T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>480000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>59</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>71</UID> <ID>71</ID> <Name>Install electrical underground</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.17</WBS> <OutlineNumber>1.7.17</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-21T08:00:00</Start> <Finish>2000-07-27T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-21T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone>
<Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>59</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>72</UID> <ID>72</ID> <Name>Install plumbing underground</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.18</WBS> <OutlineNumber>1.7.18</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-21T08:00:00</Start> <Finish>2000-07-27T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-21T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>59</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>73</UID> <ID>73</ID> <Name>Install rebar and in-floor utilities</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.19</WBS> <OutlineNumber>1.7.19</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-21T08:00:00</Start> <Finish>2000-07-26T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-21T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>480000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>59</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>74</UID> <ID>74</ID> <Name>Pour 1st floor slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.20</WBS> <OutlineNumber>1.7.20</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-28T08:00:00</Start> <Finish>2000-08-02T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-28T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>70</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>73</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>71</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>72</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>75</UID> <ID>75</ID> <Name>Cure 1st floor slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.21</WBS> <OutlineNumber>1.7.21</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-03T08:00:00</Start> <Finish>2000-08-11T17:00:00</Finish> <Duration>PT56H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT56H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>74</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>76</UID> <ID>76</ID> <Name>Strip forms from 1st floor slab</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.7.22</WBS> <OutlineNumber>1.7.22</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-14T08:00:00</Start> <Finish>2000-08-15T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-14T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>75</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>77</UID> <ID>77</ID> <Name>Carpentry Work</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.8</WBS> <OutlineNumber>1.8</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-09-05T08:00:00</Start> <Finish>2000-09-25T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>78</UID> <ID>78</ID> <Name>Install exterior sheathing and metal studs</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.8.1</WBS> <OutlineNumber>1.8.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-09-05T08:00:00</Start> <Finish>2000-09-25T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-09-05T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>64</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>69</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>79</UID> <ID>79</ID> <Name>Masonry Work</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.9</WBS> <OutlineNumber>1.9</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-06-06T08:00:00</Start> <Finish>2000-11-06T17:00:00</Finish> <Duration>PT880H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>384000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT880H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>80</UID> <ID>80</ID> <Name>Rough-in plumbing at toilets and masonry walls</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.9.1</WBS> <OutlineNumber>1.9.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-16T08:00:00</Start> <Finish>2000-09-12T17:00:00</Finish> <Duration>PT160H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-16T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT160H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>76</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>14</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>81</UID> <ID>81</ID> <Name>Lay masonry at core, mechanical, and toilets</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.9.2</WBS> <OutlineNumber>1.9.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-06-06T08:00:00</Start> <Finish>2000-07-03T17:00:00</Finish> <Duration>PT160H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-06-06T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>739200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT160H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>50</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>51</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>82</UID> <ID>82</ID> <Name>Install exterior masonry work</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.9.3</WBS> <OutlineNumber>1.9.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-09-26T08:00:00</Start> <Finish>2000-10-30T17:00:00</Finish> <Duration>PT200H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-09-26T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT200H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>78</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>83</UID> <ID>83</ID> <Name>Install roof drains</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.9.4</WBS> <OutlineNumber>1.9.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-10-31T08:00:00</Start> <Finish>2000-11-01T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-10-31T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>369600</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>82</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>84</UID> <ID>84</ID> <Name>Install tile in toilet rooms</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.9.5</WBS> <OutlineNumber>1.9.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-09-13T08:00:00</Start> <Finish>2000-09-26T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-09-13T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</Is
Subproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>80</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>85</UID> <ID>85</ID> <Name>Clean masonry</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.9.6</WBS> <OutlineNumber>1.9.6</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-10-31T08:00:00</Start> <Finish>2000-11-06T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-10-31T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>384000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>82</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>86</UID> <ID>86</ID> <Name>Clean toilet room tile</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.9.7</WBS> <OutlineNumber>1.9.7</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-09-27T08:00:00</Start> <Finish>2000-10-03T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-09-27T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>84</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>87</UID> <ID>87</ID> <Name>Roofing</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.10</WBS> <OutlineNumber>1.10</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-10-31T08:00:00</Start> <Finish>2000-12-12T17:00:00</Finish> <Duration>PT248H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>360000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT248H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>88</UID> <ID>88</ID> <Name>Install flashing at parapet walls</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.10.1</WBS> <OutlineNumber>1.10.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-10-31T08:00:00</Start> <Finish>2000-11-03T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-10-31T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>360000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>82</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>89</UID> <ID>89</ID> <Name>Pour lightweight concrete roof fill</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.10.2</WBS> <OutlineNumber>1.10.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-11-06T08:00:00</Start> <Finish>2000-11-07T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-11-06T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>360000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>12</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>83</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>88</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>90</UID> <ID>90</ID> <Name>Install seamless roofing material</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.10.3</WBS> <OutlineNumber>1.10.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-11-15T08:00:00</Start> <Finish>2000-11-21T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-11-15T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>360000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>89</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>24000</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>91</UID> <ID>91</ID> <Name>Spread stone ballast on seamless roof</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.10.4</WBS> <OutlineNumber>1.10.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-11-22T08:00:00</Start> <Finish>2000-11-28T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-11-22T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>360000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>90</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>92</UID> <ID>92</ID> <Name>Set rooftop equipment</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.10.5</WBS> <OutlineNumber>1.10.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-11-29T08:00:00</Start> <Finish>2000-12-12T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-11-29T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>360000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>91</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>93</UID> <ID>93</ID> <Name>Window wall and store front closures</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.11</WBS> <OutlineNumber>1.11</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-10-31T08:00:00</Start> <Finish>2001-01-22T17:00:00</Finish> <Duration>PT480H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>24000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT480H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>94</UID> <ID>94</ID> <Name>Install window wall aluminum and glass</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.11.1</WBS> <OutlineNumber>1.11.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-10-31T08:00:00</Start> <Finish>2000-12-04T17:00:00</Finish> <Duration>PT200H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-10-31T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT200H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>82</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>95</UID> <ID>95</ID> <Name>Install interior stud walls and drywall</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.11.2</WBS> <OutlineNumber>1.11.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-12-05T08:00:00</Start> <Finish>2001-01-08T17:00:00</Finish> <Duration>PT200H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-12-05T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT200H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>94</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>96</UID> <ID>96</ID> <Name>Install interior doors and hardware</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.11.3</WBS> <OutlineNumber>1.11.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-01-09T08:00:00</Start> <Finish>2001-01-22T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-01-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>24000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>95</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>97</UID> <ID>97</ID> <Name>Install store front doors and hardware</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.11.4</WBS> <OutlineNumber>1.11.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-10-31T08:00:00</Start> <Finish>2000-11-20T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-10-31T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>168000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>82</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject>
<LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>98</UID> <ID>98</ID> <Name>Building Finishes</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12</WBS> <OutlineNumber>1.12</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-12-05T08:00:00</Start> <Finish>2001-03-26T17:00:00</Finish> <Duration>PT640H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>33600</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT640H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>99</UID> <ID>99</ID> <Name>Install millwork and wood trim</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.1</WBS> <OutlineNumber>1.12.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-01-09T08:00:00</Start> <Finish>2001-01-29T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-01-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>97</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>95</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>100</UID> <ID>100</ID> <Name>Paint walls and woodwork</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.2</WBS> <OutlineNumber>1.12.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-01-30T08:00:00</Start> <Finish>2001-02-26T17:00:00</Finish> <Duration>PT160H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-01-30T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT160H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>99</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>96</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>101</UID> <ID>101</ID> <Name>Install conduit at ceiling plenum space</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.3</WBS> <OutlineNumber>1.12.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-12-05T08:00:00</Start> <Finish>2000-12-25T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-12-05T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>120000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>94</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>102</UID> <ID>102</ID> <Name>Install duct in ceiling plenum space</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.4</WBS> <OutlineNumber>1.12.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-01-09T08:00:00</Start> <Finish>2001-01-29T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-01-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>96000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>95</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>101</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>103</UID> <ID>103</ID> <Name>Install ceiling grid</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.5</WBS> <OutlineNumber>1.12.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-01-30T08:00:00</Start> <Finish>2001-02-12T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-01-30T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>96000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>95</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>102</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>104</UID> <ID>104</ID> <Name>Install ceiling tile</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.6</WBS> <OutlineNumber>1.12.6</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-02-13T08:00:00</Start> <Finish>2001-02-26T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-02-13T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>96000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>103</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>105</UID> <ID>105</ID> <Name>Hang wallpaper</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.7</WBS> <OutlineNumber>1.12.7</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-02-13T08:00:00</Start> <Finish>2001-02-26T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-02-13T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>96000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>103</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>106</UID> <ID>106</ID> <Name>Install building carpet</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.8</WBS> <OutlineNumber>1.12.8</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-02-27T08:00:00</Start> <Finish>2001-03-26T17:00:00</Finish> <Duration>PT160H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-02-27T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT160H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>100</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>107</UID> <ID>107</ID> <Name>Install hardware and accessories</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.9</WBS> <OutlineNumber>1.12.9</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-02-27T08:00:00</Start> <Finish>2001-03-19T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-02-27T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>24000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>100</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>108</UID> <ID>108</ID> <Name>Complete interior and exterior sod and plantings</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.10</WBS> <OutlineNumber>1.12.10</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-02-27T08:00:00</Start> <Finish>2001-03-12T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-02-27T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>33600</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>100</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>109</UID> <ID>109</ID> <Name>Pave, curb, and stripe parking lot</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.12.11</WBS> <OutlineNumber>1.12.11</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-03-13T08:00:00</Start> <Finish>2001-03-26T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-03-13T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>33600</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>108</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>110</UID> <ID>110</ID> <Name>Elevators</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.13</WBS> <OutlineNumber>1.13</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-07-04T08:00:00</Start> <Finish>2000-08-28T17:00:00</Finish> <Duration>PT320H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>739200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT320H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>111</UID> <ID>111</ID> <Name>Set elevator equipment in shafts</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.13.1</WBS> <OutlineNumber>1.13.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-0
4T08:00:00</Start> <Finish>2000-07-31T17:00:00</Finish> <Duration>PT160H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-04T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>739200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT160H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>81</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>46</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>13</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>112</UID> <ID>112</ID> <Name>Set equipment in mechanical room</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.13.2</WBS> <OutlineNumber>1.13.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-01T08:00:00</Start> <Finish>2000-08-14T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-01T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>739200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>111</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>113</UID> <ID>113</ID> <Name>Test and align doors and equipment</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.13.3</WBS> <OutlineNumber>1.13.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-15T08:00:00</Start> <Finish>2000-08-28T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-15T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>739200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>112</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>114</UID> <ID>114</ID> <Name>Plumbing</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.14</WBS> <OutlineNumber>1.14</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-11-07T08:00:00</Start> <Finish>2001-03-12T17:00:00</Finish> <Duration>PT720H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>48000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT720H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>115</UID> <ID>115</ID> <Name>Rough-in plumbing in drywall walls</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.14.1</WBS> <OutlineNumber>1.14.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-12-05T08:00:00</Start> <Finish>2001-01-01T17:00:00</Finish> <Duration>PT160H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-12-05T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>168000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT160H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>94</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>116</UID> <ID>116</ID> <Name>Tie-in fire line riser and set valves</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.14.2</WBS> <OutlineNumber>1.14.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-11-07T08:00:00</Start> <Finish>2000-11-20T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-11-07T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>384000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>85</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>117</UID> <ID>117</ID> <Name>Set plumbing fixtures and trim</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.14.3</WBS> <OutlineNumber>1.14.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-01-02T08:00:00</Start> <Finish>2001-01-22T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-01-02T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>168000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>86</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>115</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>80</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>118</UID> <ID>118</ID> <Name>Flush, test, and clean piping and fixtures</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.14.4</WBS> <OutlineNumber>1.14.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-02-27T08:00:00</Start> <Finish>2001-03-12T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-02-27T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>48000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>100</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>116</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>117</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>119</UID> <ID>119</ID> <Name>Electrical</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.15</WBS> <OutlineNumber>1.15</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-08-16T08:00:00</Start> <Finish>2001-02-26T17:00:00</Finish> <Duration>PT1112H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>110400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT1112H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>120</UID> <ID>120</ID> <Name>Rough-in electrical in masonry walls</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.15.1</WBS> <OutlineNumber>1.15.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-16T08:00:00</Start> <Finish>2000-09-12T17:00:00</Finish> <Duration>PT160H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-16T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>475200</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT160H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>76</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>15</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>121</UID> <ID>121</ID> <Name>Rough-in electrical in drywall walls</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.15.2</WBS> <OutlineNumber>1.15.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-12-05T08:00:00</Start> <Finish>2001-01-01T17:00:00</Finish> <Duration>PT160H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-12-05T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>168000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT160H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>94</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>122</UID> <ID>122</ID> <Name>Pull wire in conduit and set area transformers</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.15.3</WBS> <OutlineNumber>1.15.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-12-26T08:00:00</Start> <Finish>2001-01-15T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-12-26T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>120000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>120</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>101</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>123</UID> <ID>123</ID> <Name>Install and terminate electrical devices</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.15.4</WBS> <OutlineNumber>1.15.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-01-16T08:00:00</Start> <Finish>2001-02-05T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-01-16T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>120000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>122</PredecessorUID>
<Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>121</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>124</UID> <ID>124</ID> <Name>Make electrical terminations for HVAC equipment</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.15.5</WBS> <OutlineNumber>1.15.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-01-16T08:00:00</Start> <Finish>2001-01-17T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-01-16T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>244800</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>122</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>92</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>125</UID> <ID>125</ID> <Name>Install light fixtures - test and clean</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.15.6</WBS> <OutlineNumber>1.15.6</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-02-13T08:00:00</Start> <Finish>2001-02-26T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-02-13T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>96000</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>103</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>123</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>126</UID> <ID>126</ID> <Name>Heating and Ventilating - AC</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.16</WBS> <OutlineNumber>1.16</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2000-07-04T08:00:00</Start> <Finish>2001-03-12T17:00:00</Finish> <Duration>PT1440H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>158400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT1440H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>127</UID> <ID>127</ID> <Name>Set equipment in mechanical room</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.16.1</WBS> <OutlineNumber>1.16.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-07-04T08:00:00</Start> <Finish>2000-07-17T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-07-04T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>806400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>81</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>16</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>128</UID> <ID>128</ID> <Name>Rough-in mechanical in masonry walls</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.16.2</WBS> <OutlineNumber>1.16.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-08-16T08:00:00</Start> <Finish>2000-09-12T17:00:00</Finish> <Duration>PT160H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-08-16T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>609600</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT160H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>76</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>129</UID> <ID>129</ID> <Name>Rough-in mechanical in drywall walls</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.16.3</WBS> <OutlineNumber>1.16.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-12-05T08:00:00</Start> <Finish>2000-12-18T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-12-05T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>446400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>94</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>130</UID> <ID>130</ID> <Name>Install duct in building chase</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.16.4</WBS> <OutlineNumber>1.16.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2000-12-05T08:00:00</Start> <Finish>2000-12-25T17:00:00</Finish> <Duration>PT120H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-12-05T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>326400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT120H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>127</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>128</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>94</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>131</UID> <ID>131</ID> <Name>Set HVAC trim and test and balance system</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.16.5</WBS> <OutlineNumber>1.16.5</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-02-13T08:00:00</Start> <Finish>2001-03-12T17:00:00</Finish> <Duration>PT160H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-02-13T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>158400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT160H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>103</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>130</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>124</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>132</UID> <ID>132</ID> <Name>Final Clean-up and Occupancy</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.17</WBS> <OutlineNumber>1.17</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2001-01-09T08:00:00</Start> <Finish>2001-04-02T17:00:00</Finish> <Duration>PT480H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>86400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT480H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>133</UID> <ID>133</ID> <Name>Install hard tile flooring in common areas</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.17.1</WBS> <OutlineNumber>1.17.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-01-09T08:00:00</Start> <Finish>2001-01-15T17:00:00</Finish> <Duration>PT40H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-01-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>220800</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT40H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>95</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>134</UID> <ID>134</ID> <Name>Clean hard tile floors</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.17.2</WBS> <OutlineNumber>1.17.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-01-16T08:00:00</Start> <Finish>2001-01-19T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-01-16T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>220800</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>133</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>135</UID> <ID>135</ID> <Name>Remove debris from building and do final clean-up</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.17.3</WBS> <OutlineNumber>1.17.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-03-27T08:00:00</Start> <Finish>2001-03-30T17:00:00</Finish> <Duration>PT32H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-03-27T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT32H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>106</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>105</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>107</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>108</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>118</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>125</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Prede
cessorLink> <PredecessorUID>104</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>134</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>136</UID> <ID>136</ID> <Name>Substantial completion date</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.17.4</WBS> <OutlineNumber>1.17.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-04-02T08:00:00</Start> <Finish>2001-04-02T17:00:00</Finish> <Duration>PT8H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-04-02T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>86400</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT8H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>135</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>137</UID> <ID>137</ID> <Name>Complete Final Inspections</Name> <Type>1</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.18</WBS> <OutlineNumber>1.18</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2001-04-02T08:00:00</Start> <Finish>2001-04-09T17:00:00</Finish> <Duration>PT48H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2000-01-03T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT48H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>138</UID> <ID>138</ID> <Name>Complete elevator inspection and certification</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.18.1</WBS> <OutlineNumber>1.18.1</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-04-02T08:00:00</Start> <Finish>2001-04-04T17:00:00</Finish> <Duration>PT24H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-04-02T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT24H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>135</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>113</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>139</UID> <ID>139</ID> <Name>Perform architect's inspection</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.18.2</WBS> <OutlineNumber>1.18.2</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-04-05T08:00:00</Start> <Finish>2001-04-05T17:00:00</Finish> <Duration>PT8H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-04-05T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT8H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>135</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>109</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>138</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>140</UID> <ID>140</ID> <Name>Perform local building agency inspection</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.18.3</WBS> <OutlineNumber>1.18.3</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-04-06T08:00:00</Start> <Finish>2001-04-06T17:00:00</Finish> <Duration>PT8H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-04-06T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT8H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>139</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>141</UID> <ID>141</ID> <Name>Perform Fire Marshal's inspection</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.18.4</WBS> <OutlineNumber>1.18.4</OutlineNumber> <OutlineLevel>3</OutlineLevel> <Priority>500</Priority> <Start>2001-04-09T08:00:00</Start> <Finish>2001-04-09T17:00:00</Finish> <Duration>PT8H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-04-09T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT8H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>140</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>142</UID> <ID>142</ID> <Name>Complete punch list items from all inspections</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.19</WBS> <OutlineNumber>1.19</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2001-04-10T08:00:00</Start> <Finish>2001-04-23T17:00:00</Finish> <Duration>PT80H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-04-10T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT80H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>141</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>143</UID> <ID>143</ID> <Name>Obtain certificate of occupancy</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.20</WBS> <OutlineNumber>1.20</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2001-04-24T08:00:00</Start> <Finish>2001-04-25T17:00:00</Finish> <Duration>PT16H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-04-24T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT16H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>142</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>144</UID> <ID>144</ID> <Name>Issue final completion documents including warranties</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.21</WBS> <OutlineNumber>1.21</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2001-04-24T08:00:00</Start> <Finish>2001-04-24T17:00:00</Finish> <Duration>PT8H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-04-24T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>0</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <TotalSlack>4800</TotalSlack> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT8H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>142</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> <Task> <UID>145</UID> <ID>145</ID> <Name>Issue final request for payment</Name> <Type>0</Type> <IsNull>0</IsNull> <CreateDate>2026-06-04T07:06:13</CreateDate> <WBS>1.22</WBS> <OutlineNumber>1.22</OutlineNumber> <OutlineLevel>2</OutlineLevel> <Priority>500</Priority> <Start>2001-04-26T08:00:00</Start> <Finish>2001-04-26T17:00:00</Finish> <Duration>PT8H0M0S</Duration> <DurationFormat>7</DurationFormat> <Resume>2001-04-26T08:00:00</Resume> <ResumeValid>0</ResumeValid> <EffortDriven>1</EffortDriven> <Recurring>0</Recurring> <OverAllocated>0</OverAllocated> <Estimated>0</Estimated> <Milestone>0</Milestone> <Summary>0</Summary> <Critical>1</Critical> <IsSubproject>0</IsSubproject> <IsSubprojectReadOnly>0</IsSubprojectReadOnly> <ExternalTask>0</ExternalTask> <FixedCostAccrual>3</FixedCostAccrual> <PercentComplete>0</PercentComplete> <PercentWorkComplete>0</PercentWorkComplete> <RemainingDuration>PT8H0M0S</RemainingDuration> <ConstraintType>0</ConstraintType> <CalendarUID>-1</CalendarUID> <ConstraintDate>1970-01-01T00:00:00</ConstraintDate> <LevelAssignments>0</LevelAssignments> <LevelingCanSplit>0</LevelingCanSplit> <LevelingDelay>0</LevelingDelay> <LevelingDelayFormat>7</LevelingDelayFormat> <IgnoreResourceCalendar>0</IgnoreResourceCalendar> <HideBar>0</HideBar> <Rollup>0</Rollup> <EarnedValueMethod>0</EarnedValueMethod> <PredecessorLink> <PredecessorUID>143</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <PredecessorLink> <PredecessorUID>144</PredecessorUID> <Type>1</Type> <CrossProject>0</CrossProject> <LinkLag>0</LinkLag> <LagFormat>7</LagFormat> </PredecessorLink> <Active>1</Active> <Manual>0</Manual> </Task> </Tasks> <Resources> <Resource> <UID>0</UID> <ID>0</ID> <Name>未割り当て</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>未</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-03T08:00:00</Start> <Finish>2001-04-26T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>1</UID> <ID>1</ID> <Name>G.C. General Management</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-03T08:00:00</Start> <Finish>2001-04-26T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>5</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>2</UID> <ID>2</ID> <Name>G.C. Project Management</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-03T08:00:00</Start> <Finish>2001-04-26T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>6</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>3</UID> <ID>3</ID> <Name>G.C. Procurement</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-06T08:00:00</Start> <Finish>2000-01-25T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>7</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>4</UID> <ID>4</ID> <Name>G.C. Scheduler</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-05T08:00:00</Start> <Finish>2000-01-06T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>8</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>5</UID> <ID>5</ID> <Name>G.C. Accounting</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2001-04-26T08:00:00</Start> <Finish>2001-04-26T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>9</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>6</UID> <ID>6</ID> <Name>G.C. Superintendent</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-10T08:00:00</Start> <Finish>2001-04-23T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>10</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>7</UID> <ID>7</ID> <Name>G.C. Survey Crew</Name> <Type>1</Type> <IsNull>0</IsNull>
<Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-13T08:00:00</Start> <Finish>2000-03-08T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>11</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>8</UID> <ID>8</ID> <Name>G.C. Rough Carpenter Crew</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-03-17T08:00:00</Start> <Finish>2000-08-16T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>12</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>9</UID> <ID>9</ID> <Name>G.C. Labor Crew</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-10T08:00:00</Start> <Finish>2001-04-23T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>13</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>10</UID> <ID>10</ID> <Name>G.C. Concrete Crew</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-03-23T08:00:00</Start> <Finish>2000-08-22T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>14</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>11</UID> <ID>11</ID> <Name>G.C. Finish Carpenter Crew</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>G</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2001-01-09T08:00:00</Start> <Finish>2001-03-19T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>15</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>12</UID> <ID>12</ID> <Name>Site Grading Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>S</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-18T08:00:00</Start> <Finish>2000-03-22T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>16</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>13</UID> <ID>13</ID> <Name>Plumbing Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>P</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-06T08:00:00</Start> <Finish>2001-04-23T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>17</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>14</UID> <ID>14</ID> <Name>Plumbing Contractor Management</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>P</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-26T08:00:00</Start> <Finish>2000-02-08T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>18</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>15</UID> <ID>15</ID> <Name>Electric Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>E</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-06T08:00:00</Start> <Finish>2001-04-23T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>19</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>16</UID> <ID>16</ID> <Name>Electric Contractor Management</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>E</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-26T08:00:00</Start> <Finish>2000-02-08T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>20</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>17</UID> <ID>17</ID> <Name>HVAC Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>H</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-07-04T08:00:00</Start> <Finish>2001-04-23T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>21</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>18</UID> <ID>18</ID> <Name>HVAC Contractor Management</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>H</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-26T08:00:00</Start> <Finish>2000-02-08T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>22</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>19</UID> <ID>19</ID> <Name>Elevator Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>E</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-04-05T08:00:00</Start> <Finish>2001-04-04T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>23</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>20</UID> <ID>20</ID> <Name>Elevator Contractor Management</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>E</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-26T08:00:00</Start> <Finish>2000-02-08T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>24</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>21</UID> <ID>21</ID> <Name>Steel Erection Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>S</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-21T08:00:00</Start> <Finish>2000-06-26T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>25</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>22</UID> <ID>22</ID> <Name>Steel Erection Contractor Management</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>S</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-07T08:00:00</Start> <Finish>2000-04-13T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>26</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>23</UID> <ID>23</ID> <Name>Drywall Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>D</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-09-05T08:00:00</Start> <Finish>2001-04-23T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>27</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>24</UID> <ID>24</ID> <Name>Masonry Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>M</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-06-06T08:00:00</Start> <Finish>2000-11-06T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>28</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>25</UID> <ID>25</ID> <Name>Tile Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>T</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-09-13T08:00:00</Start> <Finish>2001-01-19T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>29</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>26</UID> <ID>26</ID> <Name>Roofing Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>R</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-10-31T08:00:00</Start> <Finish>2000-11-28T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>30</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>27</UID> <ID>27</ID> <Name>Roofing Contractor Management</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>R</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-01-26T08:00:00</Start> <Finish>2000-02-08T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>31</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>28</UID> <ID>28</ID> <Name>Window Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>W</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2000-10-31T08:00:00</Start> <Finish>2000-12-04T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>32</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>29</UID> <ID>29</ID> <Name>Carpet Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>C</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2001-02-27T08:00:00</Start> <Finish>2001-04-23T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>33</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>30</UID> <ID>30</ID> <Name>Landscape Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>L</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2001-02-27T08:00:00</Start> <Finish>2001-03-12T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>34</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>31</UID> <ID>31</ID> <Name>Paving Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>P</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2001-03-13T08:00:00</Start> <Finish>2001-04-23T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>35</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> <Resource> <UID>32</UID> <ID>32</ID> <Name>Painting Contractor</Name> <Type>1</Type> <IsNull>0</IsNull> <Initials>P</Initials> <Group></Group> <EmailAddress></EmailAddress> <MaxUnits>1</MaxUnits> <PeakUnits>1</PeakUnits> <OverAllocated>0</OverAllocated> <Start>2001-01-30T08:00:00</Start> <Finish>2001-04-23T17:00:00</Finish> <CanLevel>0</CanLevel> <AccrueAt>3</AccrueAt> <StandardRateFormat>2</StandardRateFormat> <OvertimeRateFormat>2</OvertimeRateFormat> <CalendarUID>36</CalendarUID> <IsGeneric>0</IsGeneric> <IsInactive>1</IsInactive> <IsEnterprise>0</IsEnterprise> <IsBudget>0</IsBudget> <AvailabilityPeriods/> </Resource> </Resources> <Assignments> <Assignment> <UID>1</UID> <TaskUID>1</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2001-04-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT2752H0M0S</RemainingWork> <Start>2000-01-03T08:00:00</Start> <Units>1</Units> <Work>PT2752H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>2</UID> <TaskUID>2</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-01-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT136H0M0S</RemainingWork> <Start>2000-01-03T08:00:00</Start> <Units>1</Units> <Work>PT136H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>3</UID> <TaskUID>3</TaskUID> <ResourceUID>1</ResourceUID> <Finish>2000-01-05T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <Start>2000-01-03T08:00:00</Start> <Units>1</Units> <Work>PT24H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>4</UID> <TaskUID>4</TaskUID> <ResourceUID>2</ResourceUID> <Finish>2000-01-04T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-01-03T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>5</UID> <TaskUID>4</TaskUID> <ResourceUID>1</ResourceUID> <Finish>2000-01-04T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT4H0M0S</RemainingWork> <Start>2000-01-03T08:00:00</Start> <Units>0.25</Units> <Work>PT4H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>6</UID> <TaskUID>5</TaskUID> <ResourceUID>2</ResourceUID> <Finish>2000-01-06T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT4H0M0S</RemainingWork> <Start>2000-01-05T08:00:00</Start> <Units>0.25</Units> <Work>PT4H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>7</UID> <TaskUID>5</TaskUID> <ResourceUID>4</ResourceUID> <Finish>2000-01-06T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-01-05T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>8</UID> <TaskUID>6</TaskUID> <ResourceUID>1</ResourceUID> <Finish>2000-01-10T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT1H36M0S</RemainingWork> <Start>2000-01-07T08:00:00</Start> <Units>0.1</Units> <Work>PT1H36M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>9</UID> <TaskUID>6</TaskUID> <ResourceUID>2</ResourceUID> <Finish>2000-01-10T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-01-07T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>10</UID> <TaskUID>7</TaskUID> <ResourceUID>2</ResourceUID> <Finish>2000-01-11T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-01-06T08:00:00</Start> <Units>0.5</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>11</UID> <TaskUID>7</TaskUID> <ResourceUID>3</ResourceUID> <Finish>2000-01-11T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-01-06T08:00:00</Start> <Units>0.5</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>12</UID> <TaskUID>8</TaskUID> <ResourceUID>2</Reso
urceUID> <Finish>2000-01-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-01-12T08:00:00</Start> <Units>0.5</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>13</UID> <TaskUID>8</TaskUID> <ResourceUID>3</ResourceUID> <Finish>2000-01-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-01-12T08:00:00</Start> <Units>0.5</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>14</UID> <TaskUID>9</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-01-06T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H0M0S</RemainingWork> <Start>2000-01-06T08:00:00</Start> <Units>1</Units> <Work>PT8H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>15</UID> <TaskUID>10</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-04-13T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT560H0M0S</RemainingWork> <Start>2000-01-07T08:00:00</Start> <Units>1</Units> <Work>PT560H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>16</UID> <TaskUID>11</TaskUID> <ResourceUID>22</ResourceUID> <Finish>2000-01-20T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-01-07T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>17</UID> <TaskUID>12</TaskUID> <ResourceUID>27</ResourceUID> <Finish>2000-02-08T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-01-26T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>18</UID> <TaskUID>13</TaskUID> <ResourceUID>20</ResourceUID> <Finish>2000-02-08T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <Start>2000-01-26T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>19</UID> <TaskUID>14</TaskUID> <ResourceUID>14</ResourceUID> <Finish>2000-02-08T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-01-26T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>20</UID> <TaskUID>15</TaskUID> <ResourceUID>16</ResourceUID> <Finish>2000-02-08T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-01-26T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>21</UID> <TaskUID>16</TaskUID> <ResourceUID>18</ResourceUID> <Finish>2000-02-08T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-01-26T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>22</UID> <TaskUID>17</TaskUID> <ResourceUID>22</ResourceUID> <Finish>2000-04-13T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT240H0M0S</RemainingWork> <Start>2000-01-21T08:00:00</Start> <Units>0.5</Units> <Work>PT240H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>23</UID> <TaskUID>17</TaskUID> <ResourceUID>21</ResourceUID> <Finish>2000-04-13T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT240H0M0S</RemainingWork> <Start>2000-01-21T08:00:00</Start> <Units>0.5</Units> <Work>PT240H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>24</UID> <TaskUID>18</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-01-19T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-01-06T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>25</UID> <TaskUID>19</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2000-01-07T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-01-06T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>26</UID> <TaskUID>20</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2000-01-07T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-01-06T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>27</UID> <TaskUID>21</TaskUID> <ResourceUID>6</ResourceUID> <Finish>2000-01-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT24H0M0S</RemainingWork> <Start>2000-01-10T08:00:00</Start> <Units>1</Units> <Work>PT24H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>28</UID> <TaskUID>21</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-01-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT2H24M0S</RemainingWork> <Start>2000-01-10T08:00:00</Start> <Units>0.1</Units> <Work>PT2H24M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>29</UID> <TaskUID>22</TaskUID> <ResourceUID>7</ResourceUID> <Finish>2000-01-17T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT24H0M0S</RemainingWork> <Start>2000-01-13T08:00:00</Start> <Units>1</Units> <Work>PT24H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>30</UID> <TaskUID>23</TaskUID> <ResourceUID>12</ResourceUID> <Finish>2000-01-19T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-01-18T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>31</UID> <TaskUID>23</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-01-19T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT1H36M0S</RemainingWork> <Start>2000-01-18T08:00:00</Start> <Units>0.1</Units> <Work>PT1H36M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>32</UID> <TaskUID>24</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-03-08T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT280H0M0S</RemainingWork> <Start>2000-01-20T08:00:00</Start> <Units>1</Units> <Work>PT280H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>33</UID> <TaskUID>25</TaskUID> <ResourceUID>12</ResourceUID> <Finish>2000-01-24T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT24H0M0S</RemainingWork> <Start>2000-01-20T08:00:00</Start> <Units>1</Units> <Work>PT24H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>34</UID> <TaskUID>26</TaskUID> <ResourceUID>12</ResourceUID> <Finish>2000-01-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-01-25T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>35</UID> <TaskUID>27</TaskUID> <ResourceUID>12</ResourceUID> <Finish>2000-02-02T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-01-27T08:00:00</Start> <Units>1</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>36</UID> <TaskUID>28</TaskUID> <ResourceUID>12</ResourceUID> <Finish>2000-02-16T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-02-03T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>37</UID> <TaskUID>29</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2000-02-16T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-02-03T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>38</UID> <TaskUID>30</TaskUID> <ResourceUID>12</ResourceUID> <Finish>2000-03-01T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-02-17T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>39</UID> <TaskUID>31</TaskUID> <ResourceUID>7</ResourceUID> <Finish>2000-03-08T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-03-02T08:00:00</Start> <Units>1</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>40</UID> <TaskUID>32</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-04-24T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT264H0M0S</RemainingWork> <Start>2000-03-09T08:00:00</Start> <Units>1</Units> <Work>PT264H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>41</UID> <TaskUID>33</TaskUID> <ResourceUID>12</ResourceUID> <Finish>2000-03-22T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-03-09T08:00:00</Start> <Units>0.5</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>42</UID> <TaskUID>34</TaskUID> <ResourceUID>12</ResourceUID> <Finish>2000-03-10T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-03-09T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>43</UID> <TaskUID>35</TaskUID> <ResourceUID>8</ResourceUID> <Finish>2000-03-28T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-03-23T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>44</UID> <TaskUID>36</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2000-03-16T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-03-13T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>45</UID> <TaskUID>36</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2000-03-16T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-03-13T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>46</UID> <TaskUID>37</TaskUID> <ResourceUID>8</ResourceUID> <Finish>2000-03-22T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-03-17T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>47</UID> <TaskUID>38</TaskUID> <ResourceUID>8</ResourceUID> <Finish>2000-04-03T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-03-29T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>48</UID> <TaskUID>39</TaskUID> <ResourceUID>10</ResourceUID> <Finish>2000-04-10T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-04-04T08:00:00</Start> <Units>1</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>49</UID> <TaskUID>40</TaskUID> <ResourceUID>10</ResourceUID> <Finish>2000-03-23T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H0M0S</RemainingWork> <Start>2000-03-23T08:00:00</Start> <Units>1</Units> <Work>PT8H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>50</UID> <TaskUID>41</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-04-03T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT5H36M0S</RemainingWork> <Start>2000-03-24T08:00:00</Start> <Units>0.1</Units> <Work>PT5H36M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>51</UID> <TaskUID>42</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-04-19T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT5H36M0S</RemainingWork> <Start>2000-04-11T08:00:00</Start> <Units>0.1</Units> <Work>PT5H36M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>52</UID> <TaskUID>43</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-04-04T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT0H48M0S</RemainingWork> <Start>2000-04-04T08:00:00</Start> <Units>0.1</Units> <Work>PT0H48M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>53</UID> <TaskUID>44</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-04-24T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT24H0M0S</RemainingWork> <Start>2000-04-20T08:00:00</Start> <Units>1</Units> <Work>PT24H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>54</UID> <TaskUID>45</TaskUID> <ResourceUID>19</ResourceUID> <Finish>2000-04-07T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT24H0M0S</RemainingWork> <Start>2000-04-05T08:00:00</Start> <Units>1</Units> <Work>PT24H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>55</UID> <TaskUID>46</TaskUID> <ResourceUID>10</ResourceUID> <Finish>2000-04-10T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H0M0S</RemainingWork> <Start>2000-04-10T08:00:00</Start> <Units>1</Units> <Work>PT8H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>56</UID> <TaskUID>47</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-06-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT360H0M0S</RemainingWork> <Start>2000-04-25T08:00:00</Start> <Units>1</Units> <Work>PT360H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>57</UID> <TaskUID>48</TaskUID> <ResourceUID>21</ResourceUID> <Finish>2000-05-08T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-04-25T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>58</UID> <TaskUID>49</TaskUID> <ResourceUID>21</ResourceUID> <Finish>2000-05-22T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-05-09T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>59</UID> <TaskUID>50</TaskUID> <ResourceUID>21</ResourceUID> <Finish>2000-05-22T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT60H0M0S</RemainingWork> <Start>2000-05-09T08:00:00</Start> <Units>0.75</Units> <Work>PT60H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>60</UID> <TaskUID>51</TaskUID> <ResourceUID>21</ResourceUID> <Finish>2000-06-05T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT60H0M0S</RemainingWork> <Start>2000-05-23T08:00:00</Start> <Units>0.75</Units> <Work>PT60H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>61</UID> <TaskUID>52</TaskUID> <ResourceUID>21</ResourceUID> <Finish>2000-06-19T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-06-06T08:00:00</Start> <Units>0.5</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>62</UID> <TaskUID>53</TaskUID> <ResourceUID>21</ResourceUID> <Finish>2000-06-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H0M0S</RemainingWork> <Start>2000-06-20T08:00:00</Start> <Units>0.2</Units> <Work>PT8H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>63</UID> <TaskUID>54</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-09-04T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT680H0M0S</RemainingWork> <Start>2000-05-09T08:00:00</Start> <Units>1</Units> <Work>PT680H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>64</UID> <TaskUID>55</TaskUID> <ResourceUID>8</ResourceUID> <Finish>2000-07-03T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-06-27T08:00:00</Start> <Units>1</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>65</UID> <TaskUID>55</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-07-03T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H0M0S</RemainingWork> <Start>2000-06-27T08:00:00</Start> <Units>0.2</Units> <Work>PT8H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>66</UID> <TaskUID>56</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-05-15T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <Fi
xedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT13H12M0S</RemainingWork> <Start>2000-05-09T08:00:00</Start> <Units>0.33</Units> <Work>PT13H12M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>67</UID> <TaskUID>56</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2000-05-15T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT13H12M0S</RemainingWork> <Start>2000-05-09T08:00:00</Start> <Units>0.33</Units> <Work>PT13H12M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>68</UID> <TaskUID>56</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2000-05-15T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT13H12M0S</RemainingWork> <Start>2000-05-09T08:00:00</Start> <Units>0.33</Units> <Work>PT13H12M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>69</UID> <TaskUID>57</TaskUID> <ResourceUID>10</ResourceUID> <Finish>2000-07-07T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-07-04T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>70</UID> <TaskUID>58</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-07-18T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT5H36M0S</RemainingWork> <Start>2000-07-10T08:00:00</Start> <Units>0.1</Units> <Work>PT5H36M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>71</UID> <TaskUID>59</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-07-20T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-07-19T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>72</UID> <TaskUID>60</TaskUID> <ResourceUID>8</ResourceUID> <Finish>2000-07-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT20H0M0S</RemainingWork> <Start>2000-07-19T08:00:00</Start> <Units>0.5</Units> <Work>PT20H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>73</UID> <TaskUID>60</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-07-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H0M0S</RemainingWork> <Start>2000-07-19T08:00:00</Start> <Units>0.2</Units> <Work>PT8H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>74</UID> <TaskUID>61</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-07-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT13H12M0S</RemainingWork> <Start>2000-07-19T08:00:00</Start> <Units>0.33</Units> <Work>PT13H12M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>75</UID> <TaskUID>61</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2000-07-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT13H12M0S</RemainingWork> <Start>2000-07-19T08:00:00</Start> <Units>0.33</Units> <Work>PT13H12M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>76</UID> <TaskUID>61</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2000-07-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT13H12M0S</RemainingWork> <Start>2000-07-19T08:00:00</Start> <Units>0.33</Units> <Work>PT13H12M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>77</UID> <TaskUID>62</TaskUID> <ResourceUID>10</ResourceUID> <Finish>2000-07-31T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-07-26T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>78</UID> <TaskUID>63</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-08-09T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT5H36M0S</RemainingWork> <Start>2000-08-01T08:00:00</Start> <Units>0.1</Units> <Work>PT5H36M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>79</UID> <TaskUID>64</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-08-11T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-08-10T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>80</UID> <TaskUID>65</TaskUID> <ResourceUID>8</ResourceUID> <Finish>2000-08-16T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-08-10T08:00:00</Start> <Units>1</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>81</UID> <TaskUID>65</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-08-16T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H0M0S</RemainingWork> <Start>2000-08-10T08:00:00</Start> <Units>0.2</Units> <Work>PT8H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>82</UID> <TaskUID>66</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-08-16T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT13H12M0S</RemainingWork> <Start>2000-08-10T08:00:00</Start> <Units>0.33</Units> <Work>PT13H12M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>83</UID> <TaskUID>66</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2000-08-16T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT13H12M0S</RemainingWork> <Start>2000-08-10T08:00:00</Start> <Units>0.33</Units> <Work>PT13H12M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>84</UID> <TaskUID>66</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2000-08-16T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT13H12M0S</RemainingWork> <Start>2000-08-10T08:00:00</Start> <Units>0.33</Units> <Work>PT13H12M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>85</UID> <TaskUID>67</TaskUID> <ResourceUID>10</ResourceUID> <Finish>2000-08-22T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-08-17T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>86</UID> <TaskUID>68</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-08-31T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT5H36M0S</RemainingWork> <Start>2000-08-23T08:00:00</Start> <Units>0.1</Units> <Work>PT5H36M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>87</UID> <TaskUID>69</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-09-04T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-09-01T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>88</UID> <TaskUID>70</TaskUID> <ResourceUID>8</ResourceUID> <Finish>2000-07-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-07-21T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>89</UID> <TaskUID>71</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2000-07-27T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-07-21T08:00:00</Start> <Units>1</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>90</UID> <TaskUID>72</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2000-07-27T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-07-21T08:00:00</Start> <Units>1</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>91</UID> <TaskUID>73</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-07-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT10H33M36S</RemainingWork> <Start>2000-07-21T08:00:00</Start> <Units>0.33</Units> <Work>PT10H33M36S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>92</UID> <TaskUID>73</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2000-07-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT10H33M36S</RemainingWork> <Start>2000-07-21T08:00:00</Start> <Units>0.33</Units> <Work>PT10H33M36S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>93</UID> <TaskUID>73</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2000-07-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT10H33M36S</RemainingWork> <Start>2000-07-21T08:00:00</Start> <Units>0.33</Units> <Work>PT10H33M36S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>94</UID> <TaskUID>74</TaskUID> <ResourceUID>10</ResourceUID> <Finish>2000-08-02T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-07-28T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>95</UID> <TaskUID>75</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-08-11T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT5H36M0S</RemainingWork> <Start>2000-08-03T08:00:00</Start> <Units>0.1</Units> <Work>PT5H36M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>96</UID> <TaskUID>76</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2000-08-15T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-08-14T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>97</UID> <TaskUID>77</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-09-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2000-09-05T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>98</UID> <TaskUID>78</TaskUID> <ResourceUID>23</ResourceUID> <Finish>2000-09-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2000-09-05T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>99</UID> <TaskUID>79</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-11-06T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT880H0M0S</RemainingWork> <Start>2000-06-06T08:00:00</Start> <Units>1</Units> <Work>PT880H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>100</UID> <TaskUID>80</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2000-09-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT160H0M0S</RemainingWork> <Start>2000-08-16T08:00:00</Start> <Units>1</Units> <Work>PT160H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>101</UID> <TaskUID>81</TaskUID> <ResourceUID>24</ResourceUID> <Finish>2000-07-03T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT160H0M0S</RemainingWork> <Start>2000-06-06T08:00:00</Start> <Units>1</Units> <Work>PT160H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>102</UID> <TaskUID>82</TaskUID> <ResourceUID>24</ResourceUID> <Finish>2000-10-30T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT200H0M0S</RemainingWork> <Start>2000-09-26T08:00:00</Start> <Units>1</Units> <Work>PT200H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>103</UID> <TaskUID>83</TaskUID> <ResourceUID>26</ResourceUID> <Finish>2000-11-01T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-10-31T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>104</UID> <TaskUID>84</TaskUID> <ResourceUID>25</ResourceUID> <Finish>2000-09-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-09-13T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>105</UID> <TaskUID>85</TaskUID> <ResourceUID>24</ResourceUID> <Finish>2000-11-06T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT20H0M0S</RemainingWork> <Start>2000-10-31T08:00:00</Start> <Units>0.5</Units> <Work>PT20H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>106</UID> <TaskUID>86</TaskUID> <ResourceUID>25</ResourceUID> <Finish>2000-10-03T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT20H0M0S</RemainingWork> <Start>2000-09-27T08:00:00</Start> <Units>0.5</Units> <Work>PT20H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>107</UID> <TaskUID>87</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-12-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT248H0M0S</RemainingWork> <Start>2000-10-31T08:00:00</Start> <Units>1</Units> <Work>PT248H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>108</UID> <TaskUID>88</TaskUID> <ResourceUID>26</ResourceUID> <Finish>2000-11-03T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2000-10-31T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>109</UID> <TaskUID>89</TaskUID> <ResourceUID>26</ResourceUID> <Finish>2000-11-07T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2000-11-06T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>110</UID> <TaskUID>90</TaskUID> <ResourceUID>26</ResourceUID> <Finish>2000-11-21T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-11-15T08:00:00</Start> <Units>1</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>111</UID> <TaskUID>91</TaskUID> <ResourceUID>26</ResourceUID> <Finish>2000-11-28T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2000-11-22T08:00:00</Start> <Units>1</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>112</UID> <TaskUID>92</TaskUID> <ResourceUID>17</ResourceUID> <Finish>2000-12-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-11-29T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>113</UID> <TaskUID>93</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2001-01-22T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT480H0M0S</RemainingWork> <Start>2000-10-31T08:00:00</Start> <Units>1</Units> <Work>PT480H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>114</UID> <TaskUID>94</TaskUID> <ResourceUID>28</ResourceUID> <Finish>2000-12-04T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT200H0M0S</RemainingWork> <Start>2000-10-31T08:00:00</Start> <Units>1</Units> <Work>PT200H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>115</UID> <TaskUID>95</TaskUID> <ResourceUID>23</ResourceUID> <Finish>2001-01-08T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT200H0M0S</RemainingWork> <Start>2000-12-05T08:00:00</Start> <Units>1</Units> <Work>PT200H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>116</UID> <TaskUID>96</TaskUID> <ResourceUID>11</ResourceUID> <Finish>2001-01-22T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2001-01-09T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>117</UID> <TaskUID>97</TaskUID> <ResourceUID>28</ResourceUID> <Finish>2000-11-20T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2000-10-31T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>118</UID> <TaskUID>98</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2001-03-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT640H0M0S</RemainingWork> <Start>2000-12-05T08:00:00</Start> <Units>1</Units> <Work>PT640H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>119</UID> <TaskUID>99</TaskUID> <ResourceUID>11</ResourceUID> <Finish>2001-01-29T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2001-01-09T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>120</UID> <TaskUID>100</TaskUID> <ResourceUID>32</ResourceUID> <Finish>2001-02-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRat
eUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT160H0M0S</RemainingWork> <Start>2001-01-30T08:00:00</Start> <Units>1</Units> <Work>PT160H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>121</UID> <TaskUID>101</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2000-12-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2000-12-05T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>122</UID> <TaskUID>102</TaskUID> <ResourceUID>17</ResourceUID> <Finish>2001-01-29T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2001-01-09T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>123</UID> <TaskUID>103</TaskUID> <ResourceUID>23</ResourceUID> <Finish>2001-02-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2001-01-30T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>124</UID> <TaskUID>104</TaskUID> <ResourceUID>23</ResourceUID> <Finish>2001-02-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2001-02-13T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>125</UID> <TaskUID>105</TaskUID> <ResourceUID>32</ResourceUID> <Finish>2001-02-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2001-02-13T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>126</UID> <TaskUID>106</TaskUID> <ResourceUID>29</ResourceUID> <Finish>2001-03-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT160H0M0S</RemainingWork> <Start>2001-02-27T08:00:00</Start> <Units>1</Units> <Work>PT160H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>127</UID> <TaskUID>107</TaskUID> <ResourceUID>11</ResourceUID> <Finish>2001-03-19T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2001-02-27T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>128</UID> <TaskUID>108</TaskUID> <ResourceUID>30</ResourceUID> <Finish>2001-03-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2001-02-27T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>129</UID> <TaskUID>109</TaskUID> <ResourceUID>31</ResourceUID> <Finish>2001-03-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2001-03-13T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>130</UID> <TaskUID>110</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2000-08-28T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT320H0M0S</RemainingWork> <Start>2000-07-04T08:00:00</Start> <Units>1</Units> <Work>PT320H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>131</UID> <TaskUID>111</TaskUID> <ResourceUID>19</ResourceUID> <Finish>2000-07-31T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT160H0M0S</RemainingWork> <Start>2000-07-04T08:00:00</Start> <Units>1</Units> <Work>PT160H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>132</UID> <TaskUID>112</TaskUID> <ResourceUID>19</ResourceUID> <Finish>2000-08-14T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-08-01T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>133</UID> <TaskUID>113</TaskUID> <ResourceUID>19</ResourceUID> <Finish>2000-08-28T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-08-15T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>134</UID> <TaskUID>114</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2001-03-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT720H0M0S</RemainingWork> <Start>2000-11-07T08:00:00</Start> <Units>1</Units> <Work>PT720H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>135</UID> <TaskUID>115</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2001-01-01T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT160H0M0S</RemainingWork> <Start>2000-12-05T08:00:00</Start> <Units>1</Units> <Work>PT160H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>136</UID> <TaskUID>116</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2000-11-20T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-11-07T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>137</UID> <TaskUID>117</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2001-01-22T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2001-01-02T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>138</UID> <TaskUID>118</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2001-03-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2001-02-27T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>139</UID> <TaskUID>119</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2001-02-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT1112H0M0S</RemainingWork> <Start>2000-08-16T08:00:00</Start> <Units>1</Units> <Work>PT1112H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>140</UID> <TaskUID>120</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2000-09-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT160H0M0S</RemainingWork> <Start>2000-08-16T08:00:00</Start> <Units>1</Units> <Work>PT160H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>141</UID> <TaskUID>121</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2001-01-01T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT160H0M0S</RemainingWork> <Start>2000-12-05T08:00:00</Start> <Units>1</Units> <Work>PT160H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>142</UID> <TaskUID>122</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2001-01-15T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2000-12-26T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>143</UID> <TaskUID>123</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2001-02-05T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2001-01-16T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>144</UID> <TaskUID>124</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2001-01-17T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2001-01-16T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>145</UID> <TaskUID>125</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2001-02-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2001-02-13T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>146</UID> <TaskUID>126</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2001-03-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT1440H0M0S</RemainingWork> <Start>2000-07-04T08:00:00</Start> <Units>1</Units> <Work>PT1440H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>147</UID> <TaskUID>127</TaskUID> <ResourceUID>17</ResourceUID> <Finish>2000-07-17T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-07-04T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>148</UID> <TaskUID>128</TaskUID> <ResourceUID>17</ResourceUID> <Finish>2000-09-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT160H0M0S</RemainingWork> <Start>2000-08-16T08:00:00</Start> <Units>1</Units> <Work>PT160H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>149</UID> <TaskUID>129</TaskUID> <ResourceUID>17</ResourceUID> <Finish>2000-12-18T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT80H0M0S</RemainingWork> <Start>2000-12-05T08:00:00</Start> <Units>1</Units> <Work>PT80H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>150</UID> <TaskUID>130</TaskUID> <ResourceUID>17</ResourceUID> <Finish>2000-12-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT120H0M0S</RemainingWork> <Start>2000-12-05T08:00:00</Start> <Units>1</Units> <Work>PT120H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>151</UID> <TaskUID>131</TaskUID> <ResourceUID>17</ResourceUID> <Finish>2001-03-12T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT160H0M0S</RemainingWork> <Start>2001-02-13T08:00:00</Start> <Units>1</Units> <Work>PT160H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>152</UID> <TaskUID>132</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2001-04-02T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT480H0M0S</RemainingWork> <Start>2001-01-09T08:00:00</Start> <Units>1</Units> <Work>PT480H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>153</UID> <TaskUID>133</TaskUID> <ResourceUID>25</ResourceUID> <Finish>2001-01-15T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT40H0M0S</RemainingWork> <Start>2001-01-09T08:00:00</Start> <Units>1</Units> <Work>PT40H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>154</UID> <TaskUID>134</TaskUID> <ResourceUID>25</ResourceUID> <Finish>2001-01-19T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2001-01-16T08:00:00</Start> <Units>0.5</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>155</UID> <TaskUID>135</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2001-03-30T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT32H0M0S</RemainingWork> <Start>2001-03-27T08:00:00</Start> <Units>1</Units> <Work>PT32H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>156</UID> <TaskUID>136</TaskUID> <ResourceUID>6</ResourceUID> <Finish>2001-04-02T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H0M0S</RemainingWork> <Start>2001-04-02T08:00:00</Start> <Units>1</Units> <Work>PT8H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>157</UID> <TaskUID>137</TaskUID> <ResourceUID>0</ResourceUID> <Finish>2001-04-09T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT48H0M0S</RemainingWork> <Start>2001-04-02T08:00:00</Start> <Units>1</Units> <Work>PT48H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>158</UID> <TaskUID>138</TaskUID> <ResourceUID>19</ResourceUID> <Finish>2001-04-04T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT24H0M0S</RemainingWork> <Start>2001-04-02T08:00:00</Start> <Units>1</Units> <Work>PT24H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>159</UID> <TaskUID>139</TaskUID> <ResourceUID>6</ResourceUID> <Finish>2001-04-05T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT4H0M0S</RemainingWork> <Start>2001-04-05T08:00:00</Start> <Units>0.5</Units> <Work>PT4H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>160</UID> <TaskUID>139</TaskUID> <ResourceUID>2</ResourceUID> <Finish>2001-04-05T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT4H0M0S</RemainingWork> <Start>2001-04-05T08:00:00</Start> <Units>0.5</Units> <Work>PT4H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>161</UID> <TaskUID>140</TaskUID> <ResourceUID>2</ResourceUID> <Finish>2001-04-06T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT4H0M0S</RemainingWork> <Start>2001-04-06T08:00:00</Start> <Units>0.5</Units> <Work>PT4H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>162</UID> <TaskUID>140</TaskUID> <ResourceUID>6</ResourceUID> <Finish>2001-04-06T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT4H0M0S</RemainingWork> <Start>2001-04-06T08:00:00</Start> <Units>0.5</Units> <Work>PT4H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>163</UID> <TaskUID>141</TaskUID> <ResourceUID>6</ResourceUID> <Finish>2001-04-09T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT4H0M0S</RemainingWork> <Start>2001-04-09T08:00:00</Start> <Units>0.5</Units> <Work>PT4H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>164</UID> <TaskUID>141</TaskUID> <ResourceUID>2</ResourceUID> <Finish>2001-04-09T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT4H0M0S</RemainingWork> <Start>2001-04-09T08:00:00</Start> <Units>0.5</Units> <Work>PT4H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>165</UID> <TaskUID>142</TaskUID> <ResourceUID>6</ResourceUID> <Finish>2001-04-23T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H48M0S</RemainingWork> <Start>2001-04-10T08:00:00</Start> <Units>0.11</Units> <Work>PT8H48M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>166</UID> <TaskUID>142</TaskUID> <ResourceUID>9</ResourceUID> <Finish>2001-04-23T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H48M0S</RemainingWork> <Start>2001-04-10T08:00:00</Start> <Units>0.11</Units> <Work>PT8H48M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>167</UID> <TaskUID>142</TaskUID> <ResourceUID>13</ResourceUID> <Finish>2001-04-23T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H48M0S</RemainingWork> <Start>2001-04-10T08:00:00</Start> <Units>0.11</Units> <Work>PT8H48M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>168</UID> <TaskUID>142</TaskUID> <ResourceUID>15</ResourceUID> <Finish>2001-04-23T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H48M0S</RemainingWork> <Start>2001-04-10T08:00:00</Start> <Units>0.11</Units> <Work>PT8H48M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>169</UID> <TaskUID>142</TaskUID> <ResourceUID>17</ResourceUID> <Finish>2001-04-23T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H48M0S</RemainingWork> <Start>2001-04-10T08:00:00</Start> <Units>0.11</Units> <Work>PT8H48M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>170</UID> <TaskUID>142</TaskUID> <ResourceUID>23</ResourceUID> <Finish>2001-04-23T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H48M0S</RemainingWork> <Start>2001-04-10T08:00:00</Start> <Units>0.11</Units> <Work>PT8H48M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>171</UID> <TaskUID>142</TaskUID> <ResourceUID>29</ResourceUID> <Finish>2001-04-23T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H48M0S</RemainingWork> <Start>2001-04-10T08:00:00</Start> <Units>0.11</Units> <Work>PT8H48M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>172</UID> <TaskUID>142</TaskUID> <ResourceUID>31</ResourceUID> <Finish>2001-04-23T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H48M0S</RemainingWork> <Start>2001-04-10T08:00:00</Start> <Units>0.11</Units> <Work>PT8H48M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>173</UID> <TaskUID>142</TaskUID> <ResourceUID>32</ResourceUID> <Finish>2001-04-23T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H48M0S</RemainingWork> <Start>2001-04-10T08:00:00</Start> <Units>0.11</Units> <Work>PT8H48M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>174</UID> <TaskUID>143</TaskUID> <ResourceUID>2</ResourceUID> <Fin
ish>2001-04-25T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT16H0M0S</RemainingWork> <Start>2001-04-24T08:00:00</Start> <Units>1</Units> <Work>PT16H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>175</UID> <TaskUID>144</TaskUID> <ResourceUID>2</ResourceUID> <Finish>2001-04-24T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT8H0M0S</RemainingWork> <Start>2001-04-24T08:00:00</Start> <Units>1</Units> <Work>PT8H0M0S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>176</UID> <TaskUID>145</TaskUID> <ResourceUID>2</ResourceUID> <Finish>2001-04-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT2H38M24S</RemainingWork> <Start>2001-04-26T08:00:00</Start> <Units>0.33</Units> <Work>PT2H38M24S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>177</UID> <TaskUID>145</TaskUID> <ResourceUID>5</ResourceUID> <Finish>2001-04-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT2H38M24S</RemainingWork> <Start>2001-04-26T08:00:00</Start> <Units>0.33</Units> <Work>PT2H38M24S</Work> <WorkContour>0</WorkContour> </Assignment> <Assignment> <UID>178</UID> <TaskUID>145</TaskUID> <ResourceUID>1</ResourceUID> <Finish>2001-04-26T17:00:00</Finish> <HasFixedRateUnits>1</HasFixedRateUnits> <FixedMaterial>0</FixedMaterial> <LevelingDelayFormat>7</LevelingDelayFormat> <RemainingWork>PT2H38M24S</RemainingWork> <Start>2001-04-26T08:00:00</Start> <Units>0.33</Units> <Work>PT2H38M24S</Work> <WorkContour>0</WorkContour> </Assignment> </Assignments> </Project>